## Sprint 1
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 1 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
79 | [Research] - Spring Framework | 76 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-10 18:11 | 2016-10-24 11:17 |  | 2 | 5
124 | [Task] - Spring MVC | 75 | Task | Closed | My Dang Thi Thao |  | 6 | 2016-10-13 14:17 | 2016-10-18 20:47 | 4 | 2
123 | [Task] - Spring tool overview | 75 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-10-13 14:11 | 2016-10-14 21:51 | 2 | 2
125 | [Task] - Spring REST | 75 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-10-13 14:19 | 2016-10-18 20:49 | 2 | 2
126 | [Research] - Spring Security | 75 | Task | Closed | Tuan Le |  | 4 | 2016-10-13 14:21 | 2016-10-21 13:10 | 4 | 2
134 | [Task] - Spring overview | 75 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-10-13 15:42 | 2016-10-13 19:53 | 2 | 2
111 | [Task] - Learn Eclipse | 75 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-10-12 22:17 | 2016-10-13 10:09 | 1 | 2
145 | [Task] - Research Maven | 75 | Task | Closed | My Dang Thi Thao |  | 4 | 2016-10-17 11:08 | 2016-10-18 08:58 | 3 | 2
87 | [Research] - Environment configuration | 75 | User Story | Closed | Tuan Le |  |  | 2016-10-10 18:14 | 2016-10-21 18:14 |  | 2 | 3
105 | [Task] - Config Git on desktop & Workflow | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-10-12 09:50 | 2016-10-13 13:45 | 3 | 2
106 | [Task] - Config SourceTree | 75 | Task | Closed | My Dang Thi Thao |  |  | 2016-10-12 09:51 | 2016-10-12 21:57 | 0.5 | 2
108 | [Task] - Git Proxy Config | 75 | Task | Closed | Tuan Le |  | 3 | 2016-10-12 10:04 | 2016-10-13 13:52 | 3 | 2
109 | [Task] - Eclipse Proxy Config | 75 | Task | Closed | Tuan Le |  | 2 | 2016-10-12 10:06 | 2016-10-12 15:55 | 2 | 2
139 | [Task] -Install JDK, Add TEE and GIT into STS (Spring Tool Suite) | 75 | Task | Closed | Tuan Le |  | 3 | 2016-10-14 10:08 | 2016-10-14 17:10 | 5 | 2
122 | [Task] - Write a brief guide Basic Command for Git work on STS | 75 | Task | Closed | Tuan Le |  | 3 | 2016-10-13 13:47 | 2016-10-14 11:00 | 3 | 2
148 | [Task] - Configure Maven | 75 | Task | Closed | Quan Nguyen Anh |  |  | 2016-10-18 09:09 | 2016-10-19 10:13 | 1 | 2
78 | [Research] - Team Foundation Server | 75 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-10 18:09 | 2016-10-13 15:33 |  | 2 | 2
110 | Making short manual for team to use TFS | 75 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-10-12 10:35 | 2016-10-13 15:32 | 4 | 2
91 | [Review] - Java and SCRUM | 75 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-10 18:18 | 2016-10-14 16:33 |  | 2 | 0
130 | [Task] - Java code | 75 | Task | Closed | Quan Nguyen Anh |  | 3 | 2016-10-13 14:52 | 2016-10-14 14:18 | 3 | 2
132 | [Task] - SCRUM | 75 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-10-13 14:52 | 2016-10-14 16:29 | 2 | 2
92 | [Initiation] - Proposal preparation | 76 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-11 08:17 | 2016-11-01 16:57 |  | 2 | 2
93 | [Review] - Proposal review by PM | 75 | Task | Closed | To Hoa Duy Man |  |  | 2016-10-11 08:18 | 2016-10-11 08:54 |  | 2
94 | [Issue] - Change history and version not match | 75 | Bug | Closed | Khanh Bui Nguyen Thien |  | 0.2 | 2016-10-11 08:19 | 2016-10-12 11:01 | 0.2 | 2
95 | [Issue] - Section 4.1: Collaboration tool don't use google driver. It not match with BOSCH poilicy | 75 | Bug | Closed | Khanh Bui Nguyen Thien |  | 0.2 | 2016-10-11 08:28 | 2016-10-13 08:41 | 0.2 | 2
96 | [Issue] - Please mention "Skype business" for make sure that we compatible with ISO | 75 | Bug | Closed | Khanh Bui Nguyen Thien |  | 0.2 | 2016-10-11 08:31 | 2016-10-13 08:41 | 0.2 | 2
97 | [Issue] - Section 5: CM tool is ILM - Version will be manage by ILM | 75 | Bug | Closed | Khanh Bui Nguyen Thien |  | 0.2 | 2016-10-11 08:32 | 2016-10-13 08:41 | 0.2 | 2
98 | [Issue] - Section 9: Risk Management, Please use BOSCH template | 75 | Bug | Closed | Quan Nguyen Anh | 0 | 3 | 2016-10-11 08:38 | 2016-10-13 14:35 | 3 | 2
99 | [Issue] - Missing critical computer resources (Web Server, Database server ,....) | 75 | Bug | Closed | My Dang Thi Thao | 0 | 0.5 | 2016-10-11 08:43 | 2016-10-13 08:45 | 0.5 | 2
100 | [Issue] - Section 5: Missing naming convention | 75 | Bug | Closed | Khanh Bui Nguyen Thien |  | 0.2 | 2016-10-11 08:45 | 2016-10-13 08:41 | 0.2 | 2
101 | [Issue] - Section 6: Time line should use excel or some difference tool for easy to view | 75 | Bug | Closed | My Dang Thi Thao | 0 | 1 | 2016-10-11 08:46 | 2016-10-13 08:44 | 1 | 2
121 | [Update] Proposal Release Version 1.2 | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 0.5 | 2016-10-13 13:04 | 2016-10-13 13:39 | 0.5 | 2
85 | [Research] - Prototype version 1 | 75 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-10 18:13 | 2016-10-21 17:17 |  | 2 | 5
129 | [Task] - Review Front-end Technologies | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-10-13 14:50 | 2016-10-14 15:12 | 3 | 1
128 | [Task] - Review and understand Dashboard template. | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-10-13 14:49 | 2016-10-16 10:17 | 5 | 1
131 | [Task] - Discuss and list main pages and page content | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-10-13 14:52 | 2016-10-18 09:10 | 3 | 1
135 | [Task] - Design basic template & skeleton for the prototype | 75 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-14 09:33 | 2016-10-18 09:11 | 4 | 2
136 | [Task] - Design the content of pages and team reviewed (1) | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 1 | 2016-10-14 09:49 | 2016-10-21 08:47 | 5 | 2
138 | [Task] - Design the content of pages and team reviewed (2) | 75 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-14 09:57 | 2016-10-21 15:49 | 3 | 2
141 | [Task] - Complete the Prototype Version 1 and repair for Sprint meeting Prototype present | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-10-14 11:36 | 2016-10-21 17:16 | 4 | 2
142 | [Task] Prototype Support (1) | 75 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-10-17 09:10 | 2016-10-17 10:38 | 2 | 2
143 | [Task] Prototype Support (2) | 75 | Task | Closed | Quan Nguyen Anh |  | 1 | 2016-10-17 09:10 | 2016-10-17 10:36 | 1 | 2
144 | [Task] Prototype Discussion | 75 | Task | Closed | Khanh Bui Nguyen Thien |  | 2 | 2016-10-17 09:11 | 2016-10-18 09:10 | 2 | 2
156 | [Task] - Create logical architecture | 75 | Task | Closed | My Dang Thi Thao |  | 4 | 2016-10-21 08:53 | 2016-10-21 16:21 | 4 | 2
103 | [Research] - Jmeter | 75 | User Story | Closed | Tuan Le |  |  | 2016-10-11 09:21 | 2016-10-21 18:14 |  | 2 | 2
112 | [Task] - Install and Config Jmeter to desktop | 75 | Task | Closed | Tuan Le |  |  | 2016-10-13 08:53 | 2016-10-18 14:21 | 3 | 2
113 | [Task] - Launch first test and understand the workflow | 75 | Task | Closed | Tuan Le |  |  | 2016-10-13 08:55 | 2016-10-19 10:39 | 3 | 2
149 | [Research] - What Jmeter plugin is and how to install a plugin | 75 | Task | Closed | Tuan Le |  |  | 2016-10-18 13:41 | 2016-10-18 16:56 | 4 | 2
151 | [Task] - Config for GIT to record behind Bosch Proxy | 75 | Task | Closed | Tuan Le |  |  | 2016-10-18 16:57 | 2016-10-19 09:04 | 4 | 2
102 | [Research] - Hibernate | 75 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-11 09:16 | 2016-10-21 18:14 |  | 2 | 2
133 | [Task] - Hibernate 1 | 75 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-10-13 15:06 | 2016-10-18 13:48 | 4 | 2
137 | [Task] - Hibernate 2 | 75 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-10-14 09:50 | 2016-10-19 10:47 | 4 | 2
150 | [Task] - Install MySQL and create Database | 75 | Task | Closed | Quan Nguyen Anh |  | 0 | 2016-10-18 13:49 | 2016-10-18 15:43 | 4 | 2
153 | Configurate Hibernate to STS | 75 | Task | Closed | Quan Nguyen Anh |  |  | 2016-10-19 10:48 | 2016-10-21 09:08 | 4 | 2
154 | Hibernate demo and documentation | 75 | Task | Closed | Quan Nguyen Anh |  | 0 | 2016-10-19 10:48 | 2016-10-21 10:46 | 4 | 2
119 | [Research] - MongoDB DAR | 75 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-13 09:46 | 2016-10-13 13:51 |  | 4 | 0

## Sprint 2
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 2 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
79 | [Research] - Spring Framework | 76 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-10 18:11 | 2016-10-24 11:17 |  | 2 | 5
104 | [Task] - Make a simple Spring MVC tutorial | 76 | Task | Closed | My Dang Thi Thao |  | 5 | 2016-10-12 09:28 | 2016-10-24 11:17 | 4 | 2
157 | [Research] - Spring Security (2) | 76 | Task | Closed | Tuan Le |  |  | 2016-10-21 13:10 | 2016-10-24 10:15 | 4 | 2
164 | [Research] - Spring security (3) | 76 | Task | Closed | Tuan Le |  | 4 | 2016-10-24 10:15 | 2016-10-25 15:13 | 4 | 2
193 | [Research] - Spring security (4) | 76 | Task | Closed | Tuan Le |  | 4 | 2016-10-25 15:14 | 2016-10-26 14:00 | 4 | 2
194 | [Research] - Spring Security (5) | 76 | Task | Closed | Tuan Le |  |  | 2016-10-26 14:01 | 2016-10-27 14:34 | 4 | 2
197 | [Research] - Spring security (6) | 76 | Task | Closed | Tuan Le |  |  | 2016-10-27 14:34 | 2016-11-03 11:12 | 4 | 2
198 | [Research] - Spring in Practice | 76 | Task | Closed | Tuan Le |  |  | 2016-10-28 10:26 | 2016-11-03 09:31 | 4 | 2
92 | [Initiation] - Proposal preparation | 76 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-11 08:17 | 2016-11-01 16:57 |  | 2 | 2
166 | [Task] - Rewrite about our Scope | 76 | Task | Closed | Tuan Le |  | 3 | 2016-10-24 10:19 | 2016-10-24 14:36 | 3 | 2
85 | [Research] - Prototype version 1 | 75 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-10 18:13 | 2016-10-21 17:17 |  | 2 | 5
140 | [Task] - LESS | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-14 11:33 | 2016-10-24 10:13 | 2 | 2
102 | [Research] - Hibernate | 75 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-11 09:16 | 2016-10-21 18:14 |  | 2 | 2
155 | Integrate Hibernate with Spring | 76 | Task | Closed | Quan Nguyen Anh |  | 6 | 2016-10-19 10:49 | 2016-10-27 11:14 | 4 | 2
163 | [Research] - Dashboard Spring template | 76 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:12 | 2016-11-07 08:44 |  | 2 | 2
171 | [Task] Planning for new Sprint | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:27 | 2016-10-24 10:36 | 0.5 | 2
170 | [Task] Environment setup | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:26 | 2016-10-25 12:17 | 2 | 1
173 | [Task] Research about Spring template | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:28 | 2016-11-07 08:43 | 2 | 2
179 | [Task] Migrate prototype version 1 to spring template (1) | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:30 | 2016-11-07 08:43 | 4 | 2
182 | [Task] Migrate prototype version 1 to spring template (2) | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-24 10:31 | 2016-11-07 08:43 | 4 | 2
191 | [Task] Research Apache Tiles | 76 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-10-25 12:17 | 2016-10-25 12:18 | 4 | 2
192 | [Task] Research JSF | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-10-25 12:18 | 2016-10-27 11:52 | 2 | 2
196 | [Task] Build first demo of Apache Tiles | 76 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-10-27 11:52 | 2016-10-27 11:53 | 7 | 2
208 | [Task] Research and understand Apache Tiles structure | 76 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-11-01 16:02 | 2016-11-01 16:04 | 5 | 2
209 | [Task] Adding static components using Tiles | 76 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-01 16:05 | 2016-11-01 17:13 | 2 | 2
202 | [Database] - Script and Data File schemas(1) | 77 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-31 08:29 | 2016-11-22 08:49 |  | 2 | 1
205 | [Task] - Draft schema of Script | 76 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-10-31 16:05 | 2016-11-03 11:16 | 4 | 2
177 | [Analyze] - A simple test management prototype | 76 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-24 10:30 | 2016-10-24 16:24 |  | 2 | 1
183 | [Task] - Sketch the prototype | 76 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-10-24 11:19 | 2016-10-24 14:28 | 2 | 2
184 | [Task] - Naming convention best practices | 76 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-10-24 14:29 | 2016-10-24 14:39 | 1 | 2
185 | [Task] - Make Use Case Diagram | 76 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-10-24 14:40 | 2016-10-24 16:23 | 1 | 2
178 | [Database] - Test management schema | 76 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-24 10:30 | 2016-10-24 17:17 |  | 2 | 1
186 | [Task] - Draw database schema | 76 | Task | Closed | My Dang Thi Thao |  |  | 2016-10-24 16:26 | 2016-10-24 17:08 | 1 | 2
187 | [Task] - Create database | 76 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-10-24 17:07 | 2016-10-24 17:08 | 1 | 2
188 | [Task] - Rewrite SQL script | 76 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2016-10-24 17:09 | 2016-10-24 17:17 | 0.5 | 2
180 | [Implement] - Test CRUD | 77 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-24 10:31 | 2016-11-21 13:29 |  | 2 | 3
189 | [Task] - Set up project | 76 | Task | Closed | My Dang Thi Thao |  | 8 | 2016-10-24 17:18 | 2016-11-01 07:13 | 4 | 2
199 | [Task] - Run Spring MVC example | 76 | Task | Closed | My Dang Thi Thao |  | 5 | 2016-10-29 08:42 | 2016-11-01 07:13 | 3 | 2
200 | [Task] - Jmeter overview | 76 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-10-30 09:34 | 2016-10-30 14:42 | 3 | 2
201 | [Task] - Reanalyze test management problem | 76 | Task | Closed | My Dang Thi Thao |  | 7 | 2016-10-31 07:56 | 2016-11-01 07:12 | 4 | 2
210 | [Task] - Summarize Just Spring book | 76 | Task | Closed | My Dang Thi Thao |  | 8.5 | 2016-11-02 07:19 | 2016-11-02 08:29 | 5 | 2
211 | [Task] - Run Spring Template tutorial | 76 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-11-02 08:29 | 2016-11-02 10:04 | 2 | 2
213 | [Research] - Distributed builds | 76 | User Story | Closed | Tuan Le |  |  | 2016-11-03 11:11 | 2016-12-02 08:57 |  | 4 | 2
214 | [Task] - Connecting to Man's Host4 | 76 | Task | Closed | Tuan Le |  | 4 | 2016-11-03 11:16 | 2016-11-03 17:41 | 4 | 2
215 | [Task] - How to run jenkins and run Jmeter with jenkins | 76 | Task | Closed | Tuan Le |  | 4 | 2016-11-03 17:45 | 2016-11-04 14:47 | 4 | 2

## Sprint 3
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 3 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
229 | [Diagram] - Diagrams and graphs design for project mgt | 77 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-11-11 13:09 | 2016-11-21 13:28 |  | 2 | 2
230 | [Task] - Dashboard sitemap | 77 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-11-11 13:10 | 2016-11-11 13:10 | 4 | 2
231 | [Task] - Project Management sequence diagram | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-11 13:11 | 2016-11-11 17:04 | 4 | 2
232 | [Task] - Sitemap modification | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-11 17:04 | 2016-11-11 17:39 | 2 | 2
233 | [Task] - Sequence modification | 77 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-11-11 17:04 | 2016-11-21 13:28 | 2 | 2
234 | [Task] - Database modification | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-11 17:04 | 2016-11-11 17:52 | 2 | 2
524 | [Implement] - User Management Module | 77 | User Story | Closed | Tuan Le |  |  | 2017-01-06 13:35 | 2017-01-06 13:40 |  | 2 | 3
525 | [Review] - Review Java and hibernate | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:36 | 2017-01-06 13:40 |  | 2
526 | [Design] Design the User Management Module Database | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:36 | 2017-01-06 13:40 |  | 2
527 | [Task] - Create simple User Management Module With Tiles | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:38 | 2017-01-06 13:40 |  | 2
528 | [Task] - Design Admin Workflow | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:39 | 2017-01-06 13:40 |  | 2
529 | [Task] - Design User Workflow | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:39 | 2017-01-06 13:40 |  | 2
530 | [Task] - Make Register New User | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:39 | 2017-01-06 13:40 |  | 2
531 | [Task] - Make Login page | 77 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:40 | 2017-01-06 13:40 |  | 2
223 | Project Management module | 77 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-10 08:44 | 2016-11-22 08:46 |  | 2 | 3
224 | [Review] Review knowledge about Java and Hibernate of other member's documents from previous sprints | 77 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-11-10 08:45 | 2016-11-10 08:47 | 6 | 2
225 | [Design] Design the Project Management Module database. | 77 | Task | Closed | Khanh Bui Nguyen Thien |  | 2 | 2016-11-10 08:48 | 2016-11-10 08:49 | 2 | 2
226 | [Implement] Create simple Project Management Module combining with Apache Tiles structure | 77 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-11-10 08:50 | 2016-11-10 15:00 | 5 | 2
228 | [Bug] [Walk-around] Cannot generate data from database using Tiles and Hibernate | 77 | Bug | Closed | Khanh Bui Nguyen Thien |  | 6 | 2016-11-10 14:59 | 2016-11-14 08:54 |  | 2
235 | [Implement] Create Project Management DB. | 77 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-14 08:55 | 2016-11-18 16:12 | 2 | 2
236 | [Implement] Create Project Management Module with simple MVC view | 77 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-14 08:56 | 2016-11-18 16:12 | 6 | 2
237 | [Design] Create all views for Project Management Module | 77 | Task | Closed | Khanh Bui Nguyen Thien |  | 6 | 2016-11-14 08:56 | 2016-11-21 16:58 | 6 | 2
238 | [Implement] Migrate the pm module to final template. | 77 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-14 08:58 | 2016-11-22 08:45 | 6 | 2
239 | [Task] Prepare for sprint-end presentation | 77 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-14 09:01 | 2016-11-18 16:13 | 2 | 2
202 | [Database] - Script and Data File schemas(1) | 77 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-31 08:29 | 2016-11-22 08:49 |  | 2 | 1
206 | [Task] - Draft schema of Datafile (1) | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-10-31 16:05 | 2016-11-09 12:10 | 4 | 2
217 | [Task] - Modification of Script Schemas | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-07 14:46 | 2016-11-07 17:51 | 4 | 2
218 | [Task] - Script Management Diagram | 77 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-11-07 17:52 | 2016-11-08 13:24 | 4 | 2
221 | [Task] - File distributions function (1) | 77 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-11-08 13:26 | 2016-11-09 08:42 | 4 | 2
227 | [Task] - File distributions function (2) | 77 | Task | Closed | Quan Nguyen Anh |  | 7 | 2016-11-10 09:10 | 2016-11-18 13:48 | 4 | 1
251 | [Task] - File management CRUD (1) | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-18 13:49 | 2016-11-22 08:45 | 4 | 2
180 | [Implement] - Test CRUD | 77 | User Story | Closed | My Dang Thi Thao |  |  | 2016-10-24 10:31 | 2016-11-21 13:29 |  | 2 | 3
190 | [Task] - Implement parameter CRUD | 77 | Task | Closed |  |  |  | 2016-10-25 07:28 | 2016-11-22 08:49 |  | 2
216 | [Task] - Combine Spring MVC, Security, Hibernate and Tile | 77 | Task | Closed | My Dang Thi Thao |  | 7 | 2016-11-07 10:30 | 2016-11-08 11:10 | 7 | 2
207 | [Task] - Combine Hibernate and Spring MVC | 77 | Task | Closed | My Dang Thi Thao |  | 7 | 2016-11-01 07:13 | 2016-11-07 10:30 | 5 | 2
219 | [Task] - Design Admin workflow | 77 | Task | Closed | My Dang Thi Thao |  | 1.5 | 2016-11-08 07:47 | 2016-11-08 09:12 | 2 | 2
220 | [Task] - Design Database as a whole | 77 | Task | Closed | My Dang Thi Thao |  | 14 | 2016-11-08 11:11 | 2016-11-14 10:16 | 7 | 2
240 | [Task] - Define project structure | 77 | Task | Closed | My Dang Thi Thao |  | 4 | 2016-11-14 10:17 | 2016-11-17 08:51 | 2 | 2
241 | [Task] - Add Spring boot | 77 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-14 10:22 | 2016-11-18 09:39 | 1 | 2
242 | [Task] - Create Test listing jsp page | 77 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-11-14 10:23 | 2016-11-22 08:47 | 1 | 2
243 | [Task] - Make Create Test jsp page | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:23 | 2016-11-22 08:47 | 2 | 2
244 | [Task] - Make Edit Test jsp page | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:26 | 2016-11-22 08:48 | 1 | 2
245 | [Task] - Implement Create test | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:28 | 2016-11-22 08:48 | 2 | 2
246 | [Task] - Implement Edit test | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:28 | 2016-11-22 08:48 | 2 | 2
247 | [Task] - Implement List test | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:28 | 2016-11-22 08:48 | 2 | 2
248 | [Task] - Implement Delete test | 77 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-14 10:29 | 2016-11-22 08:48 | 1 | 2
249 | [Task] - Revive the database design | 77 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-11-14 11:24 | 2016-11-15 08:46 | 2 | 2
250 | [Task] - Add Freemarker View | 77 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-18 09:39 | 2016-11-22 08:49 | 3 | 2
204 | [Analyze] Script Management functions | 77 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-10-31 08:31 | 2016-11-22 08:49 |  | 2 | 1
222 | [Task] - Design Script Management workflow (1) | 77 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-09 08:43 | 2016-11-09 12:09 | 4 | 2

## Sprint 4
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 4 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
289 | [Implement] Simple JMX Script generator using Jmeter API | 80 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-12 10:04 | 2016-12-12 10:07 |  | 2 | 2
290 | [Implement] Create simple script generator function using Jmeter API | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 6 | 2016-12-12 10:07 | 2016-12-12 10:07 | 6 | 2
291 | [Proxy] Can not perform test with other websites | 80 | Bug | Closed | Khanh Bui Nguyen Thien |  | 2 | 2016-12-12 10:10 | 2016-12-12 10:10 | 2 | 2
292 | [Implement] Jmeter Test Execution | 80 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-12 10:12 | 2016-12-12 10:12 |  | 2 | 2
293 | [Implement] Create simple test run function using generated script | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-12-12 10:13 | 2016-12-12 10:14 | 6 | 2
294 | [Implement] Execute test using real-script from Client | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-12-12 10:16 | 2016-12-12 10:16 | 5 | 2
295 | [Sovled] Can not execute test run using Scripts that are generated from Client | 80 | Bug | Closed | Khanh Bui Nguyen Thien |  | 6 | 2016-12-12 10:19 | 2016-12-19 13:16 | 4 | 2
296 | [Implement] Draw graph on Jmeter Gui using generated JTL file. | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-12-12 10:27 | 2016-12-12 10:27 | 3 | 2
299 | [Solved] Can not draw graph using generated JTL file. | 80 | Bug | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-12-12 10:30 | 2016-12-19 13:16 | 4 | 2
286 | [Research] Jmeter API | 80 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-12 09:56 | 2016-12-12 09:57 |  | 2 | 1
287 | [Review] Study and understand Jmeter API | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-12-12 09:58 | 2016-12-12 09:58 | 7 | 2
288 | [Research] Research Jmeter Api best practice. | 80 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-12-12 10:03 | 2016-12-12 10:03 | 7 | 2
280 | [Refactor] - Test Management | 80 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-01 15:13 | 2016-12-05 09:01 |  | 2 | 2
281 | [Task] - Code Test related entities | 80 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-12-01 15:14 | 2016-12-05 09:01 | 2 | 2
261 | [Implement] - Script CRUD | 80 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-11-24 10:57 | 2016-12-05 08:53 |  | 4 | 3
262 | [Task] - Implement the CRUD into template | 80 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-24 11:02 | 2016-12-05 08:53 | 4 | 2
263 | [Task] - Upload function modification | 80 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-11-24 11:02 | 2016-11-25 10:27 | 4 | 2
264 | [Task] - Validations for Delete and Edit | 80 | Task | Closed | Quan Nguyen Anh |  |  | 2016-11-24 11:03 | 2016-12-05 08:53 |  | 2
255 | [Refactor] - Project management | 80 | User Story | Closed | My Dang Thi Thao |  |  | 2016-11-23 09:06 | 2016-12-05 09:02 |  | 2 | 2
256 | [Task] - Change Tiles to Freemarker template | 80 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-23 09:08 | 2016-11-24 08:56 | 5 | 2
260 | [Task] - DB: set up embedded H2 database | 80 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-24 09:29 | 2016-11-25 09:10 | 3 | 2
265 | [Task] - DB schema and data for Project, Test, Parameter | 80 | Task | Closed | My Dang Thi Thao |  |  | 2016-11-25 08:54 | 2016-11-25 10:17 | 1 | 2
267 | [Task] - Review Project Listing | 80 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-11-25 08:57 | 2016-11-26 09:26 | 1 | 2
269 | [Task] - Add Created and modified dates | 80 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-25 08:57 | 2016-12-05 09:02 | 3 | 2
270 | [Task] - Review Project update | 80 | Task | Closed | My Dang Thi Thao |  | 7 | 2016-11-25 09:00 | 2016-11-30 10:19 | 1 | 2
271 | [Task] - Review Project create | 80 | Task | Closed | My Dang Thi Thao |  | 7 | 2016-11-25 09:00 | 2016-11-30 10:18 | 1 | 2
272 | [Task] - Review Project delete | 80 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-11-25 09:00 | 2016-11-26 09:26 | 1 | 2
274 | [Task] - Add Flash message | 80 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-11-30 10:19 | 2016-11-30 13:21 | 3 | 2
165 | [Analyze] - Simple User management prototype | 80 | User Story | Closed | Tuan Le |  |  | 2016-10-24 10:18 | 2016-11-30 13:33 |  | 2 | 1
534 | [Research] - Reseach about User management workFlow | 80 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:42 | 2017-01-06 13:42 |  | 2
167 | [Database] - User mangement | 80 | User Story | Closed | Tuan Le |  |  | 2016-10-24 10:19 | 2016-11-22 08:49 |  | 2 | 2
532 | [Task] - Change User Management Database | 80 | Task | Closed | Tuan Le |  |  | 2017-01-06 13:41 | 2017-01-06 13:41 |  | 2
168 | [Implement] - User CRUD | 81 | User Story | Closed | Tuan Le |  |  | 2016-10-24 10:19 | 2016-12-19 10:36 |  | 2 | 3
275 | [Task] - Make Register New Account For New User | 80 | Task | Closed | Tuan Le |  | 4 | 2016-11-30 13:34 | 2016-12-01 10:10 | 4 | 2
276 | [Task] - Make Create New account for admin | 80 | Task | Closed | Tuan Le |  | 4 | 2016-11-30 13:45 | 2016-12-01 10:11 | 4 | 2
277 | [Task] - Make edit user for admin | 80 | Task | Closed | Tuan Le |  | 3 | 2016-11-30 13:45 | 2016-12-01 10:13 | 3 | 2
278 | [Task] - Make delete user for admin | 80 | Task | Closed | Tuan Le |  | 3 | 2016-11-30 13:46 | 2016-12-13 09:35 | 3 | 2
169 | [Test] - User management functions | 80 | User Story | Closed | Tuan Le |  |  | 2016-10-24 10:20 | 2016-11-22 08:49 |  | 2 | 1

## Sprint 5
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 5 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
309 | [Implement] - Make Jmeter run on a separate thread | 82 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-13 09:19 | 2017-01-03 08:53 |  | 2 | 3
351 | [Task] - Implement Async | 81 | Task | Closed | My Dang Thi Thao |  | 8 | 2016-12-19 14:09 | 2016-12-19 14:09 |  | 2
297 | [Implement] Upload function | 81 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-12 10:29 | 2016-12-19 09:02 |  | 2 | 3
298 | [Task] Upload with new repository and service layer - 1 | 81 | Task | Closed | Quan Nguyen Anh |  | 7 | 2016-12-12 10:30 | 2016-12-12 10:33 | 7 | 2
303 | [Task] Upload with new repository and service layer - 2 | 81 | Task | Closed | Quan Nguyen Anh |  | 7 | 2016-12-12 10:33 | 2016-12-12 10:33 | 7 | 2
300 | [Task] Put upload with test management | 81 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-12-12 10:30 | 2016-12-12 10:34 | 5 | 2
301 | [Task] Show related files of a test to dashboard ( view ) ( test_id ) | 81 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-12-12 10:31 | 2016-12-13 09:16 | 5 | 2
302 | [Task] Delete file , Download file | 81 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-12-12 10:32 | 2016-12-14 16:52 | 5 | 2
284 | [Review] - Upload script and run | 81 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-08 09:03 | 2016-12-13 09:17 |  | 2 | 2
285 | [Task] - Add Upload controller | 81 | Task | Closed | My Dang Thi Thao |  | 5 | 2016-12-08 09:03 | 2016-12-13 09:17 | 3 | 2
306 | [Research] Jmeter report chart | 81 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-12 10:45 | 2016-12-16 17:29 |  | 2 | 3
307 | [Reasearch] Research and compare chart library to display the report result | 81 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-12-12 10:46 | 2016-12-12 10:46 | 4 | 2
308 | [Implement] Generate chart from report file on dashboard | 81 | Task | Closed | Khanh Bui Nguyen Thien |  | 7 | 2016-12-12 10:49 | 2016-12-12 10:49 | 6 | 2
253 | [Jmeter] - Generate Script and Script Execution from Dashboard | 81 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-11-21 13:32 | 2016-12-12 10:40 |  | 2 | 2
304 | [Implement] Script Generate Button on Dashboard | 81 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-12-12 10:42 | 2016-12-12 10:48 | 4 | 2
305 | [Implement] Generate Report to CSV and JTL through dashboard | 81 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-12-12 10:43 | 2016-12-12 10:44 | 4 | 2
168 | [Implement] - User CRUD | 81 | User Story | Closed | Tuan Le |  |  | 2016-10-24 10:19 | 2016-12-19 10:36 |  | 2 | 3
311 | [Implement] - transfer code from jsp to ftl | 81 | Task | Closed | Tuan Le |  |  | 2016-12-13 09:36 | 2016-12-19 10:33 | 3 | 2
523 | [Task] - Fix Authorize problem when using flt | 81 | Task | Closed | Tuan Le |  |  | 2017-01-06 11:22 | 2017-01-06 11:23 |  | 2

## Sprint 6
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 6 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
419 | [Document] Documenting own functions and works | 82 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:20 | 2017-01-06 13:44 |  | 2
420 | [Doc] HLD - Project Management Module | 82 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:22 | 2016-12-22 16:42 | 5 | 2
421 | [Doc] Use Case Diagram | 82 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:23 | 2016-12-28 09:20 | 5 | 2
422 | [Doc] Use case Specification | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-12-20 16:24 | 2016-12-26 16:48 | 5 | 2
426 | [Doc] Sequence Diagram for PM module | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-12-20 16:26 | 2016-12-28 13:26 | 3 | 2
428 | [Doc] Document Script Execution | 82 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:27 | 2016-12-22 16:43 | 4 | 2
429 | [Doc] Activity Diagram for Project Management | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-12-20 16:28 | 2016-12-28 13:27 | 3 | 2
430 | [Doc] Change Use Case to new Template @@ | 82 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:29 | 2017-01-06 13:43 | 2 | 2
405 | [Docs] - Update project documents | 82 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:57 | 2017-01-03 08:54 |  | 2
406 | [Task] - Project document checklist | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:59 | 2016-12-21 18:02 | 2 | 2
407 | [Task] - Update project plan part 2 | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:59 | 2016-12-29 17:35 | 4 | 2
408 | [Task] - Create SRS template | 82 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-12-20 14:59 | 2016-12-29 08:12 | 3 | 2
409 | [Task] - Write project docs checklist | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 15:00 | 2016-12-23 17:21 | 2 | 2
452 | [Doc] - Testplan and testcases template for the project | 82 | Task | Closed | Quan Nguyen Anh |  | 3 | 2016-12-20 16:55 | 2016-12-30 18:47 | 3 | 2
451 | [Task] - Update all missing MoM from the start | 82 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-12-20 16:55 | 2016-12-27 11:13 | 4 | 2
453 | [Doc] - RACI chart for Stakeholder Management | 82 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-12-20 16:56 | 2016-12-29 14:55 | 2 | 2
474 | [Task] - Revise project proposal | 82 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-12-21 09:59 | 2016-12-21 16:35 | 3 | 2
482 | [Task] - Revise Risk management plan | 82 | Task | Closed | My Dang Thi Thao |  | 3 | 2016-12-21 18:03 | 2016-12-21 18:03 | 3 | 2
493 | [Task] - Kick-off meeting | 82 | Task | Closed | Quan Nguyen Anh |  | 1 | 2016-12-26 09:02 | 2016-12-26 10:35 | 2 | 2
496 | [Task] - Write SRS use case spec for test mgt | 82 | Task | Closed | My Dang Thi Thao |  | 4 | 2016-12-26 18:09 | 2016-12-26 18:09 | 4 | 2
338 | [Review] - Test Management Code | 82 | User Story | Closed | Tuan Le |  |  | 2016-12-19 10:35 | 2017-01-04 13:57 |  | 2 | 3
343 | [Review] - TestController | 82 | Task | Closed | Tuan Le |  | 1 | 2016-12-19 13:32 | 2016-12-20 09:57 | 1 | 2
344 | [Review] - Test entity | 82 | Task | Closed | Tuan Le |  | 1 | 2016-12-19 13:33 | 2016-12-19 17:44 | 1 | 2
345 | [Review] - TestService | 82 | Task | Closed | Tuan Le |  | 1 | 2016-12-19 13:33 | 2016-12-20 11:34 | 1 | 2
346 | [Review] - TestServiceImpl | 82 | Task | Closed | Tuan Le |  |  | 2016-12-19 13:34 | 2016-12-20 13:47 | 1 | 2
462 | [Review] - Test View | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 17:07 | 2016-12-22 16:17 |  | 2
463 | [Review] - Test edit View | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 17:07 | 2016-12-22 16:17 |  | 2
464 | [Review] -Test Create View | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 17:07 | 2016-12-22 16:35 |  | 2
465 | [Review] - Test Detail View | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 17:08 | 2016-12-22 16:35 |  | 2
337 | [Docs] - Design of User Management | 82 | User Story | Closed | Tuan Le |  |  | 2016-12-19 10:35 | 2017-01-04 13:57 |  | 2
411 | [Task] - Draw Sequence Diagram | 82 | Task | Closed | Tuan Le |  | 2 | 2016-12-20 16:17 | 2016-12-28 17:18 | 3 | 2
412 | [Task] - Update Use Case Specification | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:17 | 2016-12-26 15:12 |  | 2
415 | [Task] - Draw Activity Diagram | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:18 | 2016-12-28 17:18 |  | 2
416 | [Task] - Draw State Chart | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:18 | 2016-12-29 09:25 |  | 2
417 | [Task] - Generate Class Diagram | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:19 | 2016-12-27 09:15 |  | 2
466 | [Task] - User Management Workflow Diagram | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 17:11 | 2016-12-29 09:25 |  | 2
491 | [Task] - Draw User Management Use Case Diagram | 82 | Task | Closed | Tuan Le |  | 0 | 2016-12-22 16:36 | 2016-12-23 15:02 | 1 | 2
336 | [Test] - User management | 83 | User Story | Closed | Tuan Le |  |  | 2016-12-19 10:35 | 2017-01-04 13:58 |  | 2 | 2
423 | [Task] - Reseach About Unit Test | 82 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:25 | 2017-01-03 08:59 |  | 2
321 | [Docs] - Design of test management | 82 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-19 10:11 | 2017-01-03 08:55 |  | 2
393 | [Task] - Draw Sequence diagram | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:43 | 2017-01-24 09:03 | 1 | 2
394 | [Task] - Update Use Case | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:44 | 2016-12-26 18:06 | 4 | 2
395 | [Task] - Edit use case specification | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:44 | 2016-12-29 17:37 | 1 | 2
396 | [Task] - Draw activity diagram | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:45 | 2017-01-24 09:03 | 1 | 2
397 | [Task] - Write use case specification | 82 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-12-20 14:45 | 2016-12-29 17:36 | 1 | 2
398 | [Task] - Generate class diagram | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:46 | 2017-01-24 09:03 | 1 | 2
399 | [Task] - Draw system architecture | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:46 | 2017-01-24 09:03 | 1 | 2
495 | [Task] - Draw use case on Docupedia | 82 | Task | Closed | My Dang Thi Thao |  | 2 | 2016-12-26 18:07 | 2016-12-26 18:07 | 2 | 2
320 | [Review] - User management code | 82 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-19 10:09 | 2017-01-03 08:53 |  | 2 | 3
323 | [Review] - CurrentUserControllerAdvice | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-19 10:26 | 2016-12-20 10:00 | 0.5 | 2
324 | [Review] - LoginController | 82 | Task | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-19 10:27 | 2016-12-20 13:46 | 0.2 | 2
325 | [Review] - ProfileController | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:28 | 2016-12-20 14:02 | 0.1 | 2
326 | [Review] - UserController | 82 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2016-12-19 10:28 | 2016-12-20 14:35 | 0.5 | 2
327 | [Review] - UsersController | 82 | Task | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-19 10:28 | 2016-12-20 14:18 | 0.2 | 2
328 | [Review] - User entity | 82 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-12-19 10:29 | 2016-12-20 09:19 | 1 | 2
329 | [Review] - UserCreateForm | 82 | Task | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-19 10:29 | 2016-12-20 09:24 | 0.2 | 2
330 | [Review] - UserRepository | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:30 | 2016-12-20 09:26 | 0.1 | 2
331 | [Review] - CurrentUserService | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:30 | 2016-12-20 09:30 | 0.1 | 2
332 | [Review] - SecurityConfiguration | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:31 | 2016-12-20 09:46 | 0.1 | 2
333 | [Review] - SecurityWebApplicationInitializer | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:31 | 2016-12-20 09:50 | 0.1 | 2
334 | [Review] - UserService | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:32 | 2016-12-20 09:38 | 0.1 | 2
335 | [Review] - UserCreatorFormValidator | 82 | Task | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-19 10:32 | 2016-12-20 09:42 | 0.1 | 2
369 | [Review] - CurrentUserDetailsService class | 82 | Task | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:43 | 2016-12-20 09:45 | 0.2 | 2
359 | [Issue] - User entity : Clean commented block of code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:17 | 2016-12-22 14:43 | 0.2 | 2
360 | [Issue] - UserCreateForm : clean not use imports | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:22 | 2016-12-22 14:44 | 0.1 | 2
361 | [Issue] - UserRepository : clean not use imports | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:26 | 2016-12-22 14:44 | 0.1 | 2
362 | [Issue] - UserRepository : format code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:27 | 2016-12-22 14:48 | 0.1 | 2
363 | [Issue] - CurrentUserService : format code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:30 | 2016-12-22 14:48 | 0.1 | 2
364 | [Issue] - UserService : format code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:33 | 2016-12-22 14:51 | 0.1 | 2
365 | [Issue] - UserServiceImpl : Log message is in Vietnamese | 82 | Bug | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:34 | 2016-12-22 14:51 | 0.2 | 2
366 | [Issue] - UserService : not use imports | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:36 | 2016-12-22 14:43 | 0.1 | 2
367 | [Issue] - UserCreateFormValidator : clean code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:39 | 2016-12-22 14:51 | 0.2 | 2
370 | [Issue] - CurrentUserDetailsService : clean code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:44 | 2016-12-22 14:51 | 0.2 | 2
371 | [Issue] - SecurityConfiguration : clean code | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:46 | 2016-12-22 14:51 | 0.1 | 2
372 | [Issue] - SecurityWebApplicationInitializer : class name | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 09:49 | 2016-12-22 14:51 | 0.1 | 2
374 | [Issue] - CurrentUserControllerAdvice : clean code | 82 | Bug | Closed | My Dang Thi Thao | 0 |  | 2016-12-20 09:58 | 2016-12-22 14:43 | 0.2 | 2
376 | [Review] - LandingController | 82 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2016-12-20 11:03 | 2016-12-20 13:12 | 0.5 | 2
377 | [Issue] - LandingController : clean code | 82 | Bug | Closed | My Dang Thi Thao | 0 |  | 2016-12-20 11:13 | 2016-12-22 14:45 | 0.1 | 2
379 | [Issue] - LandingController : ambiguous variable | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.1 | 2016-12-20 13:05 | 2016-12-22 14:44 | 0.1 | 2
380 | [Issue] - LoginController : clean code | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.1 | 2016-12-20 13:45 | 2016-12-22 14:43 | 0.1 | 2
381 | [Issue] - LoginController : Redundant mapping | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.1 | 2016-12-20 13:49 | 2016-12-22 14:44 | 0.1 | 2
382 | [Issue] - ProfileController : clean code | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.2 | 2016-12-20 14:02 | 2016-12-22 14:45 | 0.2 | 2
383 | [Issue] - UsersController : code consistency | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.2 | 2016-12-20 14:15 | 2016-12-22 14:45 | 0.2 | 2
384 | [Issue] - UserController : clean code | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0 | 2016-12-20 14:20 | 2016-12-22 14:44 | 0.1 | 2
385 | [Review] - login view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:35 | 2016-12-20 16:25 | 0.5 | 2
386 | [Review] - profile edit view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:36 | 2016-12-21 09:41 | 0.5 | 2
387 | [Review] - profile view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:36 | 2016-12-21 09:41 | 0.5 | 2
388 | [Review] - register view | 82 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2016-12-20 14:37 | 2016-12-20 16:36 | 0.5 | 2
389 | [Review] - registersuccess view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:37 | 2016-12-21 09:41 | 0.5 | 2
390 | [Review] - registration view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:37 | 2016-12-21 09:41 | 0.5 | 2
391 | [Review] - user-edit view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:38 | 2016-12-20 17:44 | 0.5 | 2
392 | [Review] - userslist view | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-20 14:38 | 2016-12-20 17:38 | 1 | 2
410 | [Issue] - Lack of register credential constraints | 82 | Bug | Closed | My Dang Thi Thao | 0 | 2 | 2016-12-20 16:10 | 2016-12-28 09:39 | 2 | 2
414 | [Issue] - Logged in user can access to Login page | 82 | Bug | Closed | My Dang Thi Thao | 0 | 1 | 2016-12-20 16:18 | 2016-12-22 14:44 | 1 | 2
424 | [Issue] - Login view : username field wrong icon | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.2 | 2016-12-20 16:25 | 2016-12-22 14:44 | 0.2 | 2
431 | [Issue] - Admin user does not have any anchor to access their profile | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.2 | 2016-12-20 16:30 | 2016-12-22 14:44 |  | 2
467 | [Issue] - userslist view : footer | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.1 | 2016-12-20 17:14 | 2016-12-22 14:44 | 0.1 | 2
468 | [Issue] - Inactive user are allowed to login | 82 | Bug | Closed | My Dang Thi Thao |  |  | 2016-12-20 17:29 | 2016-12-22 14:44 |  | 2
469 | [Issue] - Create new user form : clean | 82 | Bug | Closed | My Dang Thi Thao |  | 0.1 | 2016-12-20 17:34 | 2016-12-22 14:44 | 0.1 | 2
470 | [Issue] - Edit user (UX design) | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0.2 | 2016-12-20 17:38 | 2016-12-22 14:44 |  | 2
471 | [Issue] - No response messages after finishing edit or delete (UX) | 82 | Bug | Closed | My Dang Thi Thao |  |  | 2016-12-21 09:36 | 2016-12-22 14:44 |  | 2
472 | [Issue] - Edit, add new and register success UI is not consistent with the general design | 82 | Bug | Closed | My Dang Thi Thao | 2 |  | 2016-12-21 09:43 | 2016-12-22 14:44 | 2 | 2
473 | [Task] - Check and close issues | 82 | Task | Closed | My Dang Thi Thao |  | 1 | 2016-12-21 09:48 | 2016-12-28 07:41 | 1 | 2
358 | [Issue] - User entity does not implement Serializable | 82 | Bug | Closed | My Dang Thi Thao |  | 0.2 | 2016-12-20 09:14 | 2016-12-23 17:28 | 0.2 | 2
484 | [Issue] - Show notification message when inactive users try to log in | 82 | Bug | Closed | My Dang Thi Thao | 0 | 0 | 2016-12-22 10:48 | 2016-12-22 15:02 | 2 | 2
485 | [Task] - Research and install sonar | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-22 15:15 | 2016-12-26 18:07 | 2 | 2
312 | [Research] Jmeter Report | 83 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-19 09:14 | 2017-01-06 13:44 |  | 2
313 | [Research] Convert Jmeter report to JSON | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2016-12-19 09:15 | 2016-12-20 09:46 | 3 | 2
314 | [Research] Draw graph from existed JSON | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2016-12-19 09:15 | 2016-12-20 09:49 | 4 | 2
315 | [Implement] Auto-update JSON file | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 5 | 2016-12-19 09:22 | 2016-12-23 14:14 | 5 | 2
316 | [Implement] Javascript auto update graph. | 82 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-19 09:23 | 2016-12-26 13:10 | 5 | 2
317 | [Review] Review code File Mgt - File Upload function | 83 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-19 10:00 | 2017-01-06 13:44 |  | 2
318 | [Review] Review File Controller | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 2 | 2016-12-19 10:02 | 2016-12-21 15:26 | 2 | 2
319 | [Review] Review file management function | 82 | Task | Closed | Khanh Bui Nguyen Thien |  | 2 | 2016-12-19 10:03 | 2016-12-21 16:19 | 2 | 2
309 | [Implement] - Make Jmeter run on a separate thread | 82 | User Story | Closed | My Dang Thi Thao |  |  | 2016-12-13 09:19 | 2017-01-03 08:53 |  | 2 | 3
310 | [Task] - Research multi threading solution | 82 | Task | Closed | My Dang Thi Thao |  | 4 | 2016-12-13 09:21 | 2016-12-20 14:53 | 3 | 2
483 | [Task] - Make Jmeter concurrency | 82 | Task | Closed | My Dang Thi Thao |  |  | 2016-12-22 09:17 | 2016-12-22 10:45 | 3 | 2
347 | [Review] - Project Management Code | 82 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-19 13:46 | 2017-01-06 13:30 |  | 2 | 3
352 | [Review] - ProjectController | 82 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-12-19 16:30 | 2016-12-20 11:14 | 2 | 2
353 | [Review] - Project entity | 82 | Task | Closed | Quan Nguyen Anh |  | 1 | 2016-12-19 16:31 | 2016-12-20 09:23 | 2 | 2
354 | [Review] - ProjectRepository | 82 | Task | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-19 16:47 | 2016-12-20 11:15 | 0.1 | 2
355 | [Review] - ProjectService | 82 | Task | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-19 16:48 | 2016-12-20 11:17 | 0.1 | 2
356 | [Review] - ProjectServiceImpl | 82 | Task | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-19 16:49 | 2016-12-20 11:23 | 0.1 | 2
368 | [Issue] - ProjectController : Minor problem on getProjectForm | 82 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2016-12-20 09:40 | 2017-01-24 09:03 | 0 | 2
373 | [Issue] - Project Management Module - Cannot add a User to a project | 82 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2016-12-20 09:51 | 2017-01-24 09:03 | 0 | 2
375 | [Issue] - ProjectController : Show projectDetail of non-existing project | 82 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2016-12-20 10:02 | 2017-01-24 09:03 | 0 | 2
348 | [Docs] - Design of File Management | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-19 13:46 | 2017-01-06 15:35 |  | 2
440 | [Doc] - File Management Activity diagram modification | 82 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-12-20 16:39 | 2016-12-30 14:39 | 4 | 2
441 | [Doc] - File Management Use Case | 82 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-12-20 16:40 | 2016-12-23 14:21 | 2 | 2
442 | [Doc] - File Management Class Diagram | 82 | Task | Closed | Quan Nguyen Anh |  | 3 | 2016-12-20 16:44 | 2016-12-26 10:38 | 3 | 2
443 | [Doc] - File Management State Chart Diagram | 82 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-12-20 16:44 | 2016-12-30 18:46 | 4 | 2
444 | [Doc] - File Management Script Management Schemas | 82 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-12-20 16:46 | 2016-12-26 17:32 | 4 | 2
445 | [Doc] - File Management UseCase Specification modification | 82 | Task | Closed | Quan Nguyen Anh |  |  | 2016-12-20 16:46 | 2016-12-30 18:46 | 2 | 2
446 | [Doc] - File Management Activity Diagram | 82 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-12-20 16:47 | 2016-12-21 08:58 | 7 | 2
447 | [Doc] - Detail technical document of File Management module | 82 | Task | Closed | Quan Nguyen Anh |  | 2 | 2016-12-20 16:48 | 2016-12-30 18:47 | 7 | 2
494 | [Doc] - File Management Use Case specification | 82 | Task | Closed | Quan Nguyen Anh |  | 4 | 2016-12-26 10:40 | 2016-12-26 16:31 | 4 | 2
349 | [Test] - File Management | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-19 13:46 | 2017-01-06 13:44 |  | 2 | 2
448 | [Task] - Unit Test FileController | 82 | Task | Closed | Quan Nguyen Anh |  | 7 | 2016-12-20 16:52 | 2016-12-29 17:34 | 7 | 2
449 | [Task] - Unit test File Service Layer | 82 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-12-20 16:53 | 2016-12-28 17:19 | 5 | 2
450 | [Task] - Unit Test File Repository | 82 | Task | Closed | Quan Nguyen Anh |  | 5 | 2016-12-20 16:54 | 2016-12-28 17:19 | 4 | 2

## Sprint 7
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 7 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
500 | [Docs] - Design of test mgt module | 83 | User Story | Closed | My Dang Thi Thao |  |  | 2017-01-03 11:23 | 2017-01-04 09:33 |  | 2
507 | [Task] - Draw Activity diagram | 83 | Task | Closed | My Dang Thi Thao |  | 3 | 2017-01-03 16:32 | 2017-01-03 16:34 | 2 | 2
509 | [Task] - Draw Sequence diagram | 83 | Task | Closed | My Dang Thi Thao |  | 3 | 2017-01-03 16:34 | 2017-01-03 18:32 | 2 | 2
499 | [Docs] - Test Plan | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-03 11:22 | 2017-01-13 16:09 |  | 2
520 | [Task] - Write test plan | 83 | Task | Closed | Quan Nguyen Anh |  | 4 | 2017-01-05 11:01 | 2017-01-05 13:43 | 4 | 2
498 | [Docs] - Project Plan | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-03 11:21 | 2017-01-13 16:09 |  | 2
510 | [Task] - Project Charter | 83 | Task | Closed | Quan Nguyen Anh |  | 4 | 2017-01-04 17:32 | 2017-01-04 17:32 | 4 | 2
535 | [Doc] - Progress Status Report | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-06 13:47 | 2017-01-11 14:14 | 2 | 2
538 | [Doc] - Estimation | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:51 | 2017-01-13 16:29 |  | 2
539 | [Doc] - Project Schedule | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:52 | 2017-01-13 16:29 |  | 2
540 | [Doc] - Critical Computer Resources | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:52 | 2017-01-13 16:29 |  | 2
541 | [Doc] - Functional Safety For Iso 26262 | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:53 | 2017-01-13 16:29 |  | 2
542 | [Doc] - Decision Analysis and Resolution | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:53 | 2017-01-13 16:29 |  | 2
543 | [Doc] - Engineering Lifecycle | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:53 | 2017-01-13 16:29 |  | 2
544 | [Doc] Engineering Support | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:54 | 2017-01-13 16:29 |  | 2
545 | [Doc] - FMEA | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:54 | 2017-01-13 16:29 |  | 2
546 | [Doc] - DRBFM | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:54 | 2017-01-13 16:29 |  | 2
547 | [Doc] - Usage of Open Source Software (OSS) | 83 | Task | Closed | Tuan Le |  |  | 2017-01-09 13:55 | 2017-01-13 16:29 |  | 2
548 | [Task] - 1.Introduction | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-09 17:11 | 2017-01-09 17:11 | 2 | 2
549 | [Task] - 2.Roles and Responsiblities | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-09 17:12 | 2017-01-09 17:12 | 2 | 2
550 | [Task] - 3.1 Assumptions, Dependencies, constraints | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-09 17:13 | 2017-01-09 17:13 | 2 | 2
551 | [Task] 3.2 - Resources, tools , techniques and methodologies | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-09 17:14 | 2017-01-09 17:14 | 2 | 2
552 | [Task] - Write QA | 83 | Task | Closed | My Dang Thi Thao |  | 1 | 2017-01-10 14:47 | 2017-01-10 14:47 | 1 | 2
553 | [Task] - Edit diagram | 83 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2017-01-10 14:47 | 2017-01-10 14:47 | 0.5 | 2
554 | [Task] - Draw procedures | 83 | Task | Closed | My Dang Thi Thao |  | 2 | 2017-01-10 14:48 | 2017-01-10 14:48 | 2 | 2
555 | [Doc] - Progress Status Report ( PSR ) Risk modifications | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-11 14:14 | 2017-01-11 16:07 | 2 | 2
556 | [Doc] - Progress Status Report ( PSR ) Recommendations modifications | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-11 14:15 | 2017-01-11 16:07 | 2 | 2
557 | [Doc] - Risk and Recommendation on slide modification | 83 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-11 14:16 | 2017-01-24 09:00 | 2 | 2
558 | [Doc] - Issue Log update ( from TFS ) | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-11 14:16 | 2017-01-11 16:08 | 2 | 2
497 | [Docs] - SRS | 83 | User Story | Closed |  |  |  | 2017-01-03 11:21 | 2017-01-13 16:09 |  | 2
502 | [Task] - Introduction of SRS | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-03 14:03 | 2017-01-04 17:18 | 2 | 2
503 | [Task] - Open Source Usage | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-03 14:03 | 2017-01-04 17:18 | 2 | 2
504 | [Task] - Other Requirements | 83 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-03 14:04 | 2017-01-04 17:18 | 1 | 2
505 | [Task] - Legal, Security and Confidential Requirements | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-03 14:04 | 2017-01-04 17:18 | 2 | 2
511 | [Doc] Project Execution Related Requirement | 83 | Task | Closed | Khanh Bui Nguyen Thien |  | 4 | 2017-01-05 09:09 | 2017-01-16 10:06 | 4 | 2
512 | [Doc] Data Protection and Information Security Requirements | 83 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2017-01-05 09:11 | 2017-01-16 10:06 | 4 | 2
513 | [Doc] Software Accepetance Criteria | 83 | Task | Closed | Khanh Bui Nguyen Thien |  | 3 | 2017-01-05 09:12 | 2017-01-16 10:06 | 3 | 2
506 | [Doc] - 2.1 Operational Requirements | 83 | Task | Closed | Tuan Le |  |  | 2017-01-03 15:04 | 2017-01-06 13:46 |  | 2
515 | [Doc] - 2.3 User Interface Requirements | 83 | Task | Closed | Tuan Le |  |  | 2017-01-05 09:22 | 2017-01-06 13:47 |  | 2
516 | [Doc] - 2.5 Special Charateristics | 83 | Task | Closed | Tuan Le |  |  | 2017-01-05 09:22 | 2017-01-06 13:47 |  | 2
517 | [Doc] - 2.6 Software Safety Requirements | 83 | Task | Closed | Tuan Le |  |  | 2017-01-05 09:22 | 2017-01-06 13:47 |  | 2
518 | [Doc] - Quality Assurance Activities | 83 | Task | Closed | Tuan Le |  |  | 2017-01-05 09:23 | 2017-01-06 13:47 |  | 2
519 | [Doc] - Performance Requirements | 83 | Task | Closed | Tuan Le |  |  | 2017-01-05 09:23 | 2017-01-06 13:47 |  | 2
536 | [Task] - Product quality charateristics | 83 | Task | Closed | My Dang Thi Thao |  | 2 | 2017-01-09 13:46 | 2017-01-09 13:46 | 2 | 2
537 | [Task] - Overall activity diagram | 83 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-09 13:47 | 2017-01-09 16:08 | 2 | 2
419 | [Document] Documenting own functions and works | 82 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:20 | 2017-01-06 13:44 |  | 2
425 | [Doc] Update TFS for evidents | 83 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:26 | 2017-01-16 10:05 | 1 | 2
432 | [Doc] Draw static and dynamic chart from JSON file. | 83 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:30 | 2017-01-16 10:05 | 2 | 2
433 | [Doc] Ajax using in view page to create dynamic chart | 83 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:31 | 2017-01-16 10:05 | 2 | 2
434 | [Doc] Current workflow of Jmeter report -> draw graph | 83 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:32 | 2017-01-16 10:05 | 3 | 2
336 | [Test] - User management | 83 | User Story | Closed | Tuan Le |  |  | 2016-12-19 10:35 | 2017-01-04 13:58 |  | 2 | 2
427 | [Task] - Write test classes for User Management | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:27 | 2017-01-24 09:06 |  | 2
438 | [Task] - Fix Problems | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:36 | 2017-01-24 09:06 |  | 2
454 | [Task] - Test About Validation For User | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:56 | 2017-01-24 09:06 |  | 2
455 | [Task] - Test About Register For New User | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:57 | 2017-01-24 09:06 |  | 2
456 | [Task] - Test About Security | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:57 | 2017-01-24 09:06 | 4 | 2
457 | [Task] - Test About User Manage For Admin | 83 | Task | Closed | Tuan Le |  |  | 2016-12-20 16:58 | 2017-01-24 09:06 |  | 2
435 | [Test] Project Managment | 84 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:33 | 2017-01-24 09:06 |  | 2 | 2
514 | [Implement] Config and merge with source base on GIT1 | 83 | Task | Closed | Khanh Bui Nguyen Thien |  | 2 | 2017-01-05 09:14 | 2017-01-05 09:14 | 2 | 2
312 | [Research] Jmeter Report | 83 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-19 09:14 | 2017-01-06 13:44 |  | 2
317 | [Review] Review code File Mgt - File Upload function | 83 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-19 10:00 | 2017-01-06 13:44 |  | 2
475 | [Issue] Still able to upload duplicated file without warning | 83 | Bug | Closed | Quan Nguyen Anh | 0 | 5 | 2016-12-21 14:09 | 2017-01-24 09:06 | 2 | 2
476 | [Issue] Upload not success warning | 83 | Bug | Closed | Quan Nguyen Anh |  | 1 | 2016-12-21 14:12 | 2017-01-24 09:06 | 1 | 2
477 | [Issue] The number of file size upload too long | 83 | Bug | Closed | Quan Nguyen Anh |  | 1 | 2016-12-21 14:18 | 2017-01-24 09:06 | 1 | 2
478 | [Issue] Wrong file format error | 83 | Bug | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-21 14:28 | 2017-01-24 09:06 | 0.1 | 2
479 | [Issue] Static File Location in Database | 83 | Bug | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-21 14:55 | 2017-01-24 09:06 | 0.1 | 2
480 | [Issue] Please merge and format Fileservice | 83 | Bug | Closed | Quan Nguyen Anh |  | 0.5 | 2016-12-21 15:11 | 2017-01-24 09:06 | 0.5 | 2
481 | [Issue] Modify convertExtension() function | 83 | Bug | Closed | Quan Nguyen Anh |  | 0.1 | 2016-12-21 15:17 | 2017-01-24 09:06 | 0.1 | 2
492 | [Task] - Check and Close Issue | 83 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-22 16:41 | 2017-01-06 15:36 | 2 | 2
348 | [Docs] - Design of File Management | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-19 13:46 | 2017-01-06 15:35 |  | 2
501 | [Task] - Sequence diagram | 83 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-01-03 11:27 | 2017-01-11 14:07 | 2 | 2
349 | [Test] - File Management | 83 | User Story | Closed | Quan Nguyen Anh |  |  | 2016-12-19 13:46 | 2017-01-06 13:44 |  | 2 | 2

## Sprint 8
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 8 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
581 | [Implement] - Load reports from database | 84 | User Story | Closed | My Dang Thi Thao |  |  | 2017-01-16 09:02 | 2017-01-23 15:02 |  | 2
588 | [Task] - Implement data access classes | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:09 | 2017-01-19 16:07 | 4 | 2
590 | [Task] - Implement Json converter for report details | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:09 | 2017-01-20 14:37 | 4 | 2
603 | [Task] - Save Jtl file to database in real time | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:14 | 2017-01-19 16:07 | 8 | 2
604 | [Task] - Fix loss data problem | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:15 | 2017-01-20 17:49 | 8 | 2
605 | [Task] - Resolve problems | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:17 | 2017-01-19 16:07 | 4 | 2
606 | [Task] - Implement web service for test report | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:17 | 2017-01-23 15:01 | 3 | 2
580 | [Design] - Load reports from database | 84 | User Story | Active | My Dang Thi Thao |  |  | 2017-01-16 09:02 |  |  | 2
585 | [Task] - Design DB for reports | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:07 | 2017-01-19 16:08 | 3 | 2
586 | [Task] - Update MySQL schema | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:08 | 2017-01-24 13:37 | 4 | 2
597 | [Task] - Write brief summary of the design | 84 | Task | New | My Dang Thi Thao | 1 |  | 2017-01-16 10:12 |  | 1 | 2
599 | [Task] - Research Spring Auditing | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:13 | 2017-01-24 15:40 | 3 | 2
638 | [Task] - Implement Audit for Report | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-24 15:40 | 2017-01-24 15:40 | 3 | 2
639 | [Task] - Convert DateTime | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-25 09:37 | 2017-01-25 10:00 | 2 | 2
640 | [Task] - Research Auth2 | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-25 10:00 | 2017-01-25 13:50 | 2 | 2
579 | [Analyze] - Load reports from database | 84 | User Story | Closed | My Dang Thi Thao |  |  | 2017-01-16 09:02 | 2017-01-23 15:02 |  | 2
583 | [Research] - How to save timeseries to database | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:06 | 2017-01-16 13:58 | 4 | 2
584 | [Research] - Integrate DB with Jmeter | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:07 | 2017-01-19 16:08 | 3 | 2
622 | [Task] - Research REST api | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:29 | 2017-01-20 13:24 | 2 | 2
574 | [Test] - View test run history | 84 | User Story | New |  |  |  | 2017-01-16 08:48 |  |  | 2
582 | [Test] - Load reports from database | 84 | User Story | New | My Dang Thi Thao |  |  | 2017-01-16 09:03 |  |  | 2
593 | [Task] - Manual testing | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:11 | 2017-01-23 15:01 | 3 | 2
595 | [Task] - Do manual testing | 84 | Task | Closed | My Dang Thi Thao |  |  | 2017-01-16 10:11 | 2017-01-23 15:01 | 4 | 2
578 | [Test] - Group charts by transactions | 84 | User Story | New |  |  |  | 2017-01-16 08:52 |  |  | 2
631 | [Task] - Manual Test | 84 | Task | New |  | 4 |  | 2017-01-16 11:03 |  |  | 2
632 | [Task] - Unit Test | 84 | Task | New |  | 4 |  | 2017-01-16 11:03 |  |  | 2
577 | [Implement] - Group charts by transactions | 84 | User Story | Closed | Tuan Le |  |  | 2017-01-16 08:52 | 2017-02-16 11:22 |  | 2
633 | [Task] - Implement Controller | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:04 |  |  | 2
634 | [Task] - Implement Font-end | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:04 |  |  | 2
635 | [Task] - Fix Problem | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:05 |  |  | 2
637 | [Task] - Implement Chart | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:06 |  |  | 2
576 | [Design] - Group charts by transactions | 84 | User Story | New |  |  |  | 2017-01-16 08:52 |  |  | 2
575 | [Analyze] - Group charts by transactions | 84 | User Story | Closed | Tuan Le |  |  | 2017-01-16 08:51 | 2017-02-16 11:22 |  | 2
636 | [Research]- Research About Group By Transactions | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:05 |  |  | 2
596 | [USR] - Merge Charts | 84 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:12 | 2017-02-07 08:36 |  | 2
598 | [Test] - Merge charts | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:13 | 2017-02-07 08:36 | 1 | 2
600 | [Implement] - Merge charts | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:13 | 2017-02-07 08:37 | 4 | 2
601 | [Design] - Merge charts | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:14 | 2017-02-07 08:37 | 2 | 2
602 | [Analyze] - Merge charts | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:14 | 2017-01-16 17:18 | 1 | 2
616 | [Test] - Test script execution from Client | 84 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:27 | 2017-01-16 17:17 |  | 2
617 | [Test] - Test and compare jmx script from Client | 84 | Task | Closed | Khanh Bui Nguyen Thien |  | 6 | 2017-01-16 10:28 | 2017-01-16 17:17 | 4 | 2
566 | [Test] - Export Report as Pdf | 84 | User Story | New |  |  |  | 2017-01-16 08:44 |  |  | 2
623 | [Task] - Manual Test | 84 | Task | New |  |  |  | 2017-01-16 10:40 |  |  | 2
624 | [Taks] - Unit Test | 84 | Task | New |  |  |  | 2017-01-16 10:40 |  |  | 2
565 | [Implement] - Export Report as Pdf | 84 | User Story | Closed | Tuan Le |  |  | 2017-01-16 08:44 | 2017-02-16 11:22 |  | 2
626 | [Task] - Implement Controller | 84 | Task | Closed | Tuan Le |  |  | 2017-01-16 10:58 | 2017-01-25 10:08 |  | 2
627 | [Task] - Implement Font-end | 84 | Task | Closed | Tuan Le |  |  | 2017-01-16 10:59 | 2017-01-25 10:08 |  | 2
628 | [Task] - Implement PDF page | 84 | Task | Closed | Tuan Le |  |  | 2017-01-16 10:59 | 2017-01-25 10:08 |  | 2
629 | [Task] - Fix Problem | 84 | Task | New | Tuan Le | 4 |  | 2017-01-16 11:00 |  |  | 2
564 | [Design] - Export Report as Pdf | 84 | User Story | New |  |  |  | 2017-01-16 08:43 |  |  | 2
630 | [Task] - Design Font-Page | 84 | Task | New |  | 4 |  | 2017-01-16 11:02 |  |  | 2
563 | [Analyze] - Export Report as Pdf | 84 | User Story | Closed | Tuan Le |  |  | 2017-01-16 08:42 | 2017-02-16 11:22 |  | 2
625 | [Research] - Research How to export as PDF | 84 | Task | Closed | Tuan Le |  |  | 2017-01-16 10:40 | 2017-01-25 10:08 |  | 2
561 | [Implement] - Override Parameters | 85 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-16 08:39 | 2017-02-17 13:58 |  | 2
608 | [Task] - implement Controller | 84 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:24 | 2017-02-02 09:16 |  | 2
610 | [Task] - implement service | 84 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:25 | 2017-02-02 09:16 |  | 2
560 | [Design] - Override Parameters | 84 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-16 08:39 | 2017-02-02 09:16 |  | 2
619 | [Design] - Modelling the process of overriding parameters | 84 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:28 | 2017-02-02 09:16 |  | 2
559 | [Analyze] - Override Parameters | 84 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-16 08:39 | 2017-02-02 09:12 |  | 2
618 | [Research] - Research override Parameters from Jmeter | 84 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:28 | 2017-01-24 09:08 |  | 2
521 | [Implement] Deploy dashboard | 84 | User Story | Resolved | Khanh Bui Nguyen Thien |  |  | 2017-01-05 13:33 |  |  | 2
522 | [Bug] Logger Factory | 84 | Bug | Resolved | Khanh Bui Nguyen Thien |  | 1 | 2017-01-05 13:35 |  | 1 | 2
435 | [Test] Project Managment | 84 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:33 | 2017-01-24 09:06 |  | 2 | 2
436 | [Research] Acquire or research knowlegde about JUnit test | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:34 | 2017-02-02 09:15 | 3 | 2
437 | [Test] Write test class for PM module | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:35 | 2017-02-02 09:15 | 7 | 2
439 | [Fix] Fix problem of PM module from review | 84 | Task | Closed | Khanh Bui Nguyen Thien |  |  | 2016-12-20 16:36 | 2017-02-02 09:15 | 4.5 | 2

## Sprint 9
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 9 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
670 | [Research] - Distributed Testing | 85 | User Story | Closed | Tuan Le |  |  | 2017-02-16 11:23 | 2017-02-21 09:45 |  | 2
673 | [Task] - Read Jmeter Source Code | 85 | Task | Closed | Tuan Le |  | 8 | 2017-02-16 11:25 | 2017-02-16 11:26 | 8 | 3
674 | [Task] - Read Jmeter.java | 85 | Task | Closed | Tuan Le |  |  | 2017-02-16 11:25 | 2017-02-21 09:45 |  | 2
669 | [Implement] - Distributed Testing | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-16 11:23 | 2017-03-21 14:23 |  | 2
689 | [Task] - implement Distributed Testing | 85 | Task | Closed | Tuan Le |  | 8 | 2017-02-21 09:46 | 2017-02-21 09:47 | 8 | 4
690 | [Task] - run Distributed Testing on multiple agents | 85 | Task | Closed | Tuan Le |  | 8 | 2017-02-21 09:47 | 2017-02-21 09:49 | 8 | 4
664 | [Test] - Unit Testing for Test , Project , User , File Modules | 85 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-02-08 09:21 | 2017-02-21 08:44 |  | 2
665 | [Task] - Unit Test for Test Management | 85 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-02-08 09:22 | 2017-02-17 13:59 | 8 | 2
666 | [Task] - Unit Test for Project Management | 85 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-02-08 09:22 | 2017-02-17 13:58 | 8 | 2
667 | [Task] - Unit Test for User Management | 85 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-02-08 09:22 | 2017-02-17 13:58 | 8 | 2
668 | [Task] - Unit Test for File Management | 85 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-08 09:23 | 2017-02-13 10:21 | 4 | 2
645 | [Implement] - Group management | 85 | User Story | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:56 | 2017-02-21 09:48 |  | 2
656 | [Task] - Implement Spring Data for Group management | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:06 | 2017-02-17 13:28 | 4 | 2
657 | [Task] - Implement the view of group management | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:06 | 2017-02-17 13:28 | 4 | 2
658 | [Task] - Implement group controller | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:07 | 2017-02-17 13:28 | 4 | 2
659 | [Task] - Refine the group mamangement implementation | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:08 | 2017-02-17 13:28 | 4 | 2
660 | [Task] - Update changes on the dashboard design | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:08 | 2017-02-17 13:28 | 2 | 2
644 | [Design] - Group management | 85 | User Story | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:56 | 2017-02-21 09:44 |  | 2
654 | [Task] - Design db | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:04 | 2017-02-17 13:27 | 1 | 2
655 | [Task] - Update dashboard design diagram | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:05 | 2017-02-17 13:27 | 1 | 2
643 | [Analyze] - Group management | 85 | User Story | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:56 | 2017-02-21 09:44 |  | 2
652 | [Research] - Spring security ACL | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:03 | 2017-02-17 13:27 | 4 | 2
653 | [Task] - Try ACL examples | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:03 | 2017-02-17 13:27 | 2 | 2
607 | [USR] - Test report with corresponding user. | 85 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:23 | 2017-02-17 14:00 |  | 2
609 | [Analyze] - Test report with corresponding user. | 85 | Task | New | My Dang Thi Thao |  |  | 2017-01-16 10:25 |  | 1 | 2
611 | [Design] - Test report with corresponding user. | 85 | Task | New | Khanh Bui Nguyen Thien | 2 |  | 2017-01-16 10:25 |  | 2 | 2
612 | [Implement] - Test report with corresponding user. | 85 | Task | New | Khanh Bui Nguyen Thien | 6 |  | 2017-01-16 10:25 |  | 6 | 2
615 | [Test] - Test report with corresponding user. | 85 | Task | New | Khanh Bui Nguyen Thien | 1 |  | 2017-01-16 10:25 |  | 1 | 2
587 | [USR] - Test run history | 85 | User Story | Closed | Khanh Bui Nguyen Thien |  |  | 2017-01-16 10:08 | 2017-02-17 13:59 |  | 1
589 | [Implement] - View test run history | 85 | Task | New | Khanh Bui Nguyen Thien | 7 |  | 2017-01-16 10:09 |  | 7 | 2
591 | [Design] - View test run history | 85 | Task | New | Khanh Bui Nguyen Thien | 6 |  | 2017-01-16 10:10 |  | 6 | 2
592 | [Analyze] - View test run history | 85 | Task | New | Khanh Bui Nguyen Thien | 6 |  | 2017-01-16 10:10 |  | 6 | 2
594 | [Test] View test run history | 85 | Task | New | Khanh Bui Nguyen Thien | 5 |  | 2017-01-16 10:11 |  | 5 | 2
562 | [Test] - Override Parameters | 85 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-16 08:39 | 2017-02-21 08:44 |  | 2
620 | [Task] - Service Unit Testing | 85 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-01-16 10:29 | 2017-02-17 13:59 | 8 | 2
621 | [Task] - Controller Unit Testing | 85 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-01-16 10:29 | 2017-02-17 13:59 | 8 | 2
561 | [Implement] - Override Parameters | 85 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-01-16 08:39 | 2017-02-17 13:58 |  | 2
613 | [Task] - Refactor Code | 85 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:25 | 2017-02-08 09:17 |  | 2
614 | [Task] - Fix Problem | 85 | Task | Closed | Quan Nguyen Anh |  |  | 2017-01-16 10:25 | 2017-02-13 09:00 |  | 2
662 | [Task] - Add new implementation to source code | 85 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-08 09:17 | 2017-02-09 08:41 | 8 | 2
663 | [Task] - Modify services to cover the business requirements | 85 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-08 09:18 | 2017-02-13 10:20 | 8 | 2
641 | [Refactor] - Optimize code | 85 | User Story | Closed | My Dang Thi Thao |  |  | 2017-02-06 14:36 | 2017-02-21 09:48 |  | 2
642 | [Task] - Migrate to MySQL | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-06 14:53 | 2017-02-08 08:57 | 3 | 2
646 | [Task] - Implement all entities in the db schema | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:58 | 2017-02-17 13:28 | 2 | 2
647 | [Task] - Implement FileStorage | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:59 | 2017-02-17 13:28 | 4 | 2
648 | [Task] - Refactor controllers | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 08:59 | 2017-02-17 13:28 | 7 | 2
649 | [Task] - Refactor Spring Data | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:00 | 2017-02-17 13:28 | 7 | 2
650 | [Task] - Refactor Jmeter code | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:00 | 2017-02-17 13:28 | 7 | 2
651 | [Task] - Fix security bugs | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:01 | 2017-02-17 13:28 | 7 | 2
661 | [Task] - Set up new dashboard for Jar deployment | 85 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-08 09:09 | 2017-02-08 09:09 | 4 | 2

## Sprint 10
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 10 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
738 | [Analyse] - Graph Calculations | 88 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:35 | 2017-03-27 09:00 |  | 2
739 | [Task] - Analyse Calculation for Thread Per Second Metrics | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:36 | 2017-03-06 11:31 | 7 | 2
740 | [Task] - Calculation for Response Time Over Time metrics | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:37 | 2017-02-27 08:16 | 7 | 2
741 | [Task] - Calculation for Hits Per Second metrics | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:37 | 2017-03-06 11:32 | 7 | 2
742 | [Task] - Calculation for Throughput metrics | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:38 | 2017-03-06 11:32 | 4 | 2
720 | [Implement] - Implement Graph calculation | 87 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-02-22 10:23 | 2017-03-17 13:05 |  | 2
724 | [Task] - Implement Static Active Threads Per Second | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 10:26 | 2017-02-27 08:20 | 4 | 2
736 | [Bug] - Static Respond Time Over Time Graph metrics | 86 | Bug | Closed | Quan Nguyen Anh | 0 | 4 | 2017-02-22 11:33 | 2017-02-27 08:17 | 4 | 2
716 | [Review] - Review Charts and Data Metrics | 86 | User Story | New | Quan Nguyen Anh |  |  | 2017-02-22 09:11 |  |  | 2
717 | [Review] - Review real-time report and static reports | 86 | Task | Closed | Quan Nguyen Anh |  | 8 | 2017-02-22 09:13 | 2017-02-22 09:13 | 8 | 2
718 | [Review] - Review calculation of graph metrics compare with Jmeter plugins | 86 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 09:14 | 2017-02-27 08:16 | 8 | 2
675 | Bug list | 89 | User Story | New |  |  |  | 2017-02-21 09:06 |  |  | 2
692 | [Bug] - Dropdown list to choose group in project form does not save | 86 | Bug | Closed | My Dang Thi Thao | 4 |  | 2017-02-21 09:50 | 2017-02-21 09:53 | 4 | 2
696 | [Bug] - Project cannot save new group when edit | 86 | Bug | Closed | My Dang Thi Thao | 4 |  | 2017-02-21 13:04 | 2017-02-21 13:25 | 4 | 2
676 | Issue list | 89 | User Story | New |  |  |  | 2017-02-21 09:08 |  |  | 2
712 | [Issue] - Unclear workflow of admin | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:20 | 2017-02-27 09:10 | 3 | 2
715 | [Issue] - Views are full with undeveloped feature causing confusion | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:22 | 2017-02-27 09:10 | 4 | 2
719 | [Issue] - Request mappings are not well-structured for project | 86 | Task | Closed | My Dang Thi Thao |  | 7 | 2017-02-22 09:43 | 2017-02-24 10:24 | 4 | 2
743 | [Issue] - Jmeter config management view for Admin | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-27 14:24 | 2017-02-28 14:26 | 3 | 2
744 | [Issue] - Report management view for admin | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-28 14:26 | 2017-02-28 18:41 | 3 | 2
745 | [Issue] - Test management view for admin | 86 | Task | Closed | My Dang Thi Thao |  | 3 | 2017-02-28 18:42 | 2017-03-01 13:26 | 5 | 2
677 | [Design] - Test History | 86 | User Story | Closed | My Dang Thi Thao |  |  | 2017-02-21 09:08 | 2017-03-21 14:29 |  | 2
693 | [Task] - Draw prototype for test history | 86 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2017-02-21 09:51 | 2017-02-21 09:53 | 0.5 | 2
694 | [Task] - Create view for test history | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 09:51 | 2017-02-21 09:53 | 2 | 2
680 | [Analyze] - Authorization roles | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:09 |  |  | 2
701 | [Task] - Analyze the workflow | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:09 | 2017-03-01 13:26 | 1 | 2
702 | [Task] - Research authorization solution | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:09 | 2017-03-01 15:17 | 2 | 2
682 | [Implement] - Authorization roles | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:10 |  |  | 2
698 | [Task] - Implement Admin panel | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 17:58 | 2017-02-21 17:58 | 2 | 2
706 | [Task] - Implement admin area for user management | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:11 | 2017-03-01 15:17 | 3 | 2
685 | [Implement] - Granted Authority | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:14 |  |  | 2
708 | [Task] - Classify links | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 18:18 | 2017-02-27 14:23 | 3 | 2
684 | [Design] - Granted Authority | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:13 |  |  | 2
697 | [Task] - Design Admin home page | 86 | Task | Closed | My Dang Thi Thao |  |  | 2017-02-21 17:57 | 2017-02-21 17:57 | 0.5 | 2

## Sprint 11
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 11 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
757 | [Implement] - Scheduler | 87 | User Story | New |  |  |  | 2017-03-07 11:02 |  |  | 2
756 | [Analyze] - Scheduler | 87 | User Story | New |  |  |  | 2017-03-07 11:02 |  |  | 2
747 | Non-Delivery | 89 | User Story | Closed |  |  |  | 2017-03-06 15:25 | 2017-03-21 14:29 |  | 2
748 | [My] - Sprint planning | 87 | Task | Closed | My Dang Thi Thao |  | 1 | 2017-03-06 15:28 | 2017-03-07 09:33 | 1 | 2
749 | [Tuesday] - Daily and plan | 87 | Task | Closed | My Dang Thi Thao |  | 0.5 | 2017-03-07 09:33 | 2017-03-08 09:14 |  | 2
746 | Non-Effort | 89 | User Story | Active |  |  |  | 2017-03-06 15:22 |  |  | 2
750 | [My] - Validation team weekly meeting | 87 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-07 09:34 | 2017-03-08 09:14 | 1.5 | 2
763 | [Quan] - Women's Day Celebration | 87 | Task | Closed | Quan Nguyen Anh |  | 0 | 2017-03-08 14:15 | 2017-03-08 14:16 | 1 | 2
728 | [Implement] - Implement Agents Management | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-22 10:34 | 2017-03-21 14:23 |  | 2
732 | [Task] - Implement Agents Management | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:37 | 2017-03-21 14:22 |  | 2
733 | [Task] - Create Agents Management Controller | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:43 | 2017-03-21 14:22 |  | 2
727 | [Design] - Agents Management | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-22 10:33 | 2017-03-21 14:23 |  | 2
730 | [Task] - Draw prototype for Agents Management | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:36 | 2017-03-21 14:23 |  | 2
731 | [Task] - Create View For Agents Management | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:36 | 2017-03-08 10:46 |  | 2
720 | [Implement] - Implement Graph calculation | 87 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-02-22 10:23 | 2017-03-17 13:05 |  | 2
721 | [Task] - Implement Real-time graph Respond Time Over Milliseconds | 87 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-02-22 10:24 | 2017-03-09 09:32 | 2 | 2
722 | [Task] - Implement Static Hits per Second Graph | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 10:25 | 2017-03-08 08:56 | 2 | 2
723 | [Task] - Implement Static Threads Over Time | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-02-22 10:25 | 2017-03-07 13:42 | 2 | 2
735 | [Bug] - Static Hit Per Second Graph metrics | 87 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-02-22 11:33 | 2017-03-09 09:32 | 2 | 2
737 | [Bug] - Outliers value from multiple graphs | 87 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-02-22 11:34 | 2017-03-17 13:05 | 7 | 2
758 | [Issue] - Account expired , config environment for STS to deploy project | 87 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-03-07 13:42 | 2017-03-07 16:30 | 1 | 2
760 | [Task] - Hits per seconds - Calculation test | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-08 08:57 | 2017-03-09 09:31 | 2 | 2
764 | [Task] - Implement Static Throughput Graph | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-09 09:40 | 2017-03-10 12:46 | 2 | 2
765 | [Task] - Add report tabs for static graphs on report page | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-09 09:45 | 2017-03-17 13:05 | 2 | 2
768 | [Task] - Revise the graphs because the X axis show wrong statistics | 87 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-10 12:46 | 2017-03-14 13:47 | 2 | 2
672 | [Implement] - Distributed Testing Font-end | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-16 11:24 | 2017-03-21 14:23 |  | 2
695 | [Task] - implement distributed Fond-end | 87 | Task | Closed | Tuan Le |  | 0 | 2017-02-21 09:58 | 2017-03-06 16:20 | 8 | 2
671 | [Design] - Distributed Testing Font-end | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-16 11:24 | 2017-03-21 14:23 |  | 2
725 | [Task] - Draw prototype for Distributed Test | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:32 | 2017-03-08 10:46 |  | 2
726 | [Task] - Create view for Distributed test | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:32 | 2017-03-08 10:46 |  | 2
669 | [Implement] - Distributed Testing | 87 | User Story | Closed | Tuan Le |  |  | 2017-02-16 11:23 | 2017-03-21 14:23 |  | 2
691 | [Bug] - read the csv file | 87 | Bug | Closed | Tuan Le | 3 |  | 2017-02-21 09:49 | 2017-03-21 14:23 |  | 2
734 | [Task] - Create Distributed Testing Controller | 87 | Task | Closed | Tuan Le |  |  | 2017-02-22 10:43 | 2017-03-21 14:23 |  | 2
755 | [Summarize] - Overall about Jmeter Distributed Testing | 87 | Task | Closed | Tuan Le |  |  | 2017-03-07 11:01 | 2017-03-09 10:01 | 2 | 2
766 | [Task] - Read Quan Overwrite Parameter | 87 | Task | Closed | Tuan Le |  |  | 2017-03-09 10:00 | 2017-03-21 14:23 |  | 2
767 | [Task] - Merge Overwrite Parameter with Distributed Testing | 87 | Task | Closed | Tuan Le |  |  | 2017-03-09 10:02 | 2017-03-21 14:23 |  | 2
675 | Bug list | 89 | User Story | New |  |  |  | 2017-02-21 09:06 |  |  | 2
769 | [Bug] - Handling null return from duration and delay tag of JMX file | 87 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-03-14 13:48 | 2017-03-17 13:28 | 4 | 2
678 | [Implement] - Test history | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:09 |  |  | 2
699 | [Task] - Implement web service for test history | 87 | Task | New | My Dang Thi Thao | 4 |  | 2017-02-21 18:07 |  | 4 | 2
679 | [Analyze] - Test history | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:09 |  |  | 2
700 | [Task] - Analyze the workflow | 87 | Task | New | My Dang Thi Thao | 1 |  | 2017-02-21 18:08 |  | 1 | 2
680 | [Analyze] - Authorization roles | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:09 |  |  | 2
681 | [Design] - Authorization roles | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:09 |  |  | 2
703 | [Task] - Change sidebar view for admin | 87 | Task | Closed | My Dang Thi Thao |  | 1 | 2017-02-21 18:10 | 2017-03-07 09:34 | 1.5 | 2
704 | [Task] - Design the views | 87 | Task | New | My Dang Thi Thao | 2 |  | 2017-02-21 18:10 |  | 2 | 2
751 | [Task] - Remake project view for PM | 87 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-07 09:41 | 2017-03-07 14:17 | 1 | 2
752 | [Task] - Make group view for PM | 87 | Task | Active | My Dang Thi Thao | 1 |  | 2017-03-07 09:42 |  | 1 | 2
753 | [Task] - Make Test view for PM | 87 | Task | Active | My Dang Thi Thao | 2 |  | 2017-03-07 09:43 |  | 2 | 2
754 | [Task] - Modify test run and distributed run | 87 | Task | Active | My Dang Thi Thao | 2 |  | 2017-03-07 09:44 |  | 2 | 2
759 | [Task] - Make report views for PM | 87 | Task | Active | My Dang Thi Thao | 1 |  | 2017-03-07 14:17 |  | 1 | 2
762 | [Implement] - Three main roles: admin, pm and tester | 87 | Task | Active | My Dang Thi Thao | 2 |  | 2017-03-08 09:19 |  | 2 | 2
682 | [Implement] - Authorization roles | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:10 |  |  | 2
705 | [Task] - Implement security layer | 87 | Task | New | My Dang Thi Thao | 8 |  | 2017-02-21 18:11 |  | 8 | 2
685 | [Implement] - Granted Authority | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:14 |  |  | 2
707 | [Task] - Implement ACL | 87 | Task | New | My Dang Thi Thao | 7 |  | 2017-02-21 18:18 |  | 7 | 2
683 | [Analyse] - Granted Authoriy | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:13 |  |  | 2
709 | [Task] - Research and find solution | 87 | Task | New | My Dang Thi Thao | 4 |  | 2017-02-21 18:19 |  | 4 | 2
684 | [Design] - Granted Authority | 87 | User Story | New | My Dang Thi Thao |  |  | 2017-02-21 09:13 |  |  | 2
710 | [Task] - Design views | 87 | Task | New | My Dang Thi Thao | 2 |  | 2017-02-21 18:19 |  | 2 | 2
711 | [Task] - Design db tables | 87 | Task | New | My Dang Thi Thao | 3 |  | 2017-02-21 18:19 |  | 3 | 2

## Sprint 12
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 12 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
821 | [Implement] - Upload Script and Run It Form Homepage | 88 | User Story | Closed | Tuan Le |  |  | 2017-03-22 16:34 | 2017-04-10 15:08 |  | 2
828 | [Implement] - Create Uploader Controller | 88 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:46 | 2017-03-24 13:44 |  | 2
829 | [Implement] - Create Homepage | 88 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:46 | 2017-03-24 13:44 |  | 2
820 | [Design] - Upload Script and Run It Form Homepage | 88 | User Story | Closed | Tuan Le |  |  | 2017-03-22 16:34 | 2017-04-10 15:08 |  | 2
826 | [Design] - Design Homepage Again | 88 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:43 | 2017-03-24 13:44 |  | 2
827 | [Design] - Design Uploader Controller | 88 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:46 | 2017-03-24 13:44 |  | 2
819 | [Analyse] - Upload Script and Run It Form Homepage | 88 | User Story | Closed | Tuan Le |  |  | 2017-03-22 16:33 | 2017-04-10 15:08 |  | 2
824 | [Research] - Drag and Drop File | 88 | Task | Closed | Tuan Le |  | 5 | 2017-03-22 16:42 | 2017-03-24 13:42 |  | 2
825 | [Research]- Fine-Uploader Library | 88 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:43 | 2017-03-24 13:43 |  | 2
747 | Non-Delivery | 89 | User Story | Closed |  |  |  | 2017-03-06 15:25 | 2017-03-21 14:29 |  | 2
761 | [Wednesday] - Daily and plan | 88 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-08 09:14 | 2017-03-21 14:12 | 0.5 | 2
746 | Non-Effort | 89 | User Story | Active |  |  |  | 2017-03-06 15:22 |  |  | 2
835 | [Task] - Microservices demo | 88 | Task | Closed | Quan Nguyen Anh |  | 2 | 2017-03-24 13:43 | 2017-03-27 09:00 |  | 2
738 | [Analyse] - Graph Calculations | 88 | User Story | Closed | Quan Nguyen Anh |  |  | 2017-02-22 11:35 | 2017-03-27 09:00 |  | 2
675 | Bug list | 89 | User Story | New |  |  |  | 2017-02-21 09:06 |  |  | 2
785 | [Task] - Modify History view , previous reports of the test | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-17 14:54 | 2017-03-30 11:31 |  | 2
786 | [Bug] - Group is null when edit or run in test detail | 88 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-03-20 10:02 | 2017-04-03 13:37 |  | 2
817 | [Bug] - Duplication error when create users | 88 | Bug | Closed | Quan Nguyen Anh |  |  | 2017-03-21 15:44 | 2017-04-03 13:37 |  | 2
832 | [Bug] - CAN NOT Run Jar File | 88 | Bug | Closed | Tuan Le |  | 5 | 2017-03-23 15:17 | 2017-03-23 15:18 | 5 | 2
789 | [Analyze] - Report Analysis | 89 | User Story | New | My Dang Thi Thao |  |  | 2017-03-21 13:41 |  |  | 2 | 2
792 | [Task] - Try to extends ResultCollector | 88 | Task | Closed | My Dang Thi Thao |  | 2 | 2017-03-21 13:42 | 2017-03-21 13:44 | 2 | 2
793 | [Task] - Extract data from ReportGenerator | 88 | Task | Closed | My Dang Thi Thao |  | 6 | 2017-03-21 13:43 | 2017-03-21 13:44 | 6 | 2
794 | [Task] - Test feasibility of the new approach | 88 | Task | Closed | My Dang Thi Thao |  | 3 | 2017-03-21 13:44 | 2017-03-21 13:50 | 3 | 2
804 | [Research] - Overall metrics fomula | 88 | Task | Closed | My Dang Thi Thao |  | 1 | 2017-03-21 14:02 | 2017-03-23 18:25 | 3 | 2
676 | Issue list | 89 | User Story | New |  |  |  | 2017-02-21 09:08 |  |  | 2
770 | [Issue] - Register account is not available on the current project | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-17 13:33 | 2017-03-30 10:13 |  | 2
811 | [Implement] - User Management | 88 | User Story | New | Quan Nguyen Anh |  |  | 2017-03-21 14:12 |  |  | 2
812 | [Task] - Add field Roles to set role for each user | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-21 14:13 | 2017-03-21 15:46 | 4 | 2
813 | [Issue] - Cannot bind the role with the form | 88 | Bug | Closed | Quan Nguyen Anh | 0 |  | 2017-03-21 14:14 | 2017-03-27 09:01 | 4 | 2
814 | [Task] - Role configuration | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-21 14:14 | 2017-03-30 10:13 | 4 | 2
818 | [Task] - Create another way to bind the role to the form | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-21 15:46 | 2017-03-23 14:27 | 4 | 2
831 | [Task] - Create Role View and Role Controller | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-23 14:27 | 2017-03-24 13:42 |  | 2
834 | Modify security | 88 | Task | Closed | Quan Nguyen Anh |  |  | 2017-03-24 13:42 | 2017-03-27 17:32 |  | 2
836 | [Issue] - Cannot fetch all the roles from user | 88 | Bug | Closed | Quan Nguyen Anh |  |  | 2017-03-27 17:33 | 2017-04-03 13:36 |  | 2
790 | [Design] - Report Analysis | 88 | User Story | New | My Dang Thi Thao |  |  | 2017-03-21 13:41 |  |  | 2 | 2
795 | [Task] - Design the final report page | 88 | Task | Closed | My Dang Thi Thao |  | 7 | 2017-03-21 13:50 | 2017-03-22 16:10 | 7 | 2
796 | [Task] - Design the real time report page | 88 | Task | Closed | My Dang Thi Thao |  | 4 | 2017-03-21 13:50 | 2017-03-21 18:07 | 4 | 2
791 | [Implement] - Report Analysis | 89 | User Story | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:41 | 2017-04-30 13:03 |  | 2 | 3
800 | [Task] - Implement function for general metrics | 88 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:59 | 2017-03-28 11:22 | 7 | 2

## Sprint 13
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 13 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
822 | [Analyse] - Run Script Jmx with CSV file | 89 | User Story | Closed | Tuan Le |  |  | 2017-03-22 16:34 | 2017-04-05 16:42 |  | 2
830 | [Research] - Research How Jmeter Run script with csv File | 89 | Task | Closed | Tuan Le |  |  | 2017-03-22 16:47 | 2017-04-05 16:42 |  | 2
833 | [Research] - JMeterPluginsCMD Command Line Tool | 89 | Task | Closed | Tuan Le |  |  | 2017-03-23 17:34 | 2017-04-05 16:42 |  | 2
747 | Non-Delivery | 89 | User Story | Closed |  |  |  | 2017-03-06 15:25 | 2017-03-21 14:29 |  | 2
746 | Non-Effort | 89 | User Story | Active |  |  |  | 2017-03-06 15:22 |  |  | 2
675 | Bug list | 89 | User Story | New |  |  |  | 2017-02-21 09:06 |  |  | 2
686 | [Bug] - Report detail does note save | 89 | Bug | New | My Dang Thi Thao | 4 |  | 2017-02-21 09:15 |  | 4 | 2
687 | [Bug] - Loss records of report detail table | 89 | Bug | New | My Dang Thi Thao | 4 | 3 | 2017-02-21 09:16 |  | 7 | 2
688 | [Bug] - Null collumn in Report csv file | 89 | Bug | New | My Dang Thi Thao | 4 |  | 2017-02-21 09:16 |  | 4 | 2
771 | [Task] - Log in page modification | 89 | Task | New | Quan Nguyen Anh | 0.25 |  | 2017-03-17 13:41 |  |  | 2
772 | [Task] - Sidebar - #Project M. - Access to Test List page for specific project | 89 | Task | New | Quan Nguyen Anh | 1 |  | 2017-03-17 13:50 |  | 2 | 2
775 | [Task] - Sidebar - #Project M. - Access to Report List View for specific tests | 89 | Task | New | Quan Nguyen Anh | 0.25 |  | 2017-03-17 13:55 |  |  | 2
774 | [Task] - Sidebar - #Report M. - Access to Report Detail page for specific report | 89 | Task | New | Quan Nguyen Anh | 1 |  | 2017-03-17 13:53 |  |  | 2
776 | [Task] - Sidebar - #CreateServices - Create test/project/group pops up on sidebar | 89 | Task | New | Quan Nguyen Anh | 2 |  | 2017-03-17 14:10 |  |  | 2
778 | [Task] - Sidebar - #Test M. - Access to Test Detail page for specific recent test | 89 | Task | New | Quan Nguyen Anh | 0.25 |  | 2017-03-17 14:24 |  |  | 2
779 | [Task] - Profile - #User M. - Add User Management to the current project | 89 | Task | New | Quan Nguyen Anh | 5 |  | 2017-03-17 14:25 |  |  | 2
777 | [Task] - Content - #Project M. -Add delete and edit action on project list page | 89 | Task | New | Quan Nguyen Anh | 0.25 |  | 2017-03-17 14:11 |  |  | 2
773 | [Task] - Content - #Test M. - Test singular and multiple delete on test list | 89 | Task | New | Quan Nguyen Anh | 1 |  | 2017-03-17 13:52 |  |  | 2
780 | [Task] - Content - #Test M. - Test data show on test list | 89 | Task | New | Quan Nguyen Anh | 1 |  | 2017-03-17 14:40 |  |  | 2
782 | [Bug] - Whitelabel Error Page when not uploading JMX File , create a error message for this | 89 | Bug | New | Quan Nguyen Anh | 1 |  | 2017-03-17 14:45 |  |  | 2
783 | [Bug] - delay tag in xml not found ( Override parameter) | 89 | Bug | New | Quan Nguyen Anh | 1 |  | 2017-03-17 14:52 |  |  | 2
784 | [Bug] - Project is null when edit in test detail | 89 | Bug | New | Quan Nguyen Anh | 1 |  | 2017-03-17 14:53 |  |  | 2
787 | [Bug] - Report page has not prevent access to non-existing id | 89 | Bug | New | Quan Nguyen Anh | 1 |  | 2017-03-20 10:21 |  |  | 2
788 | [Bug] - General Real-Time report does not show data when starting | 89 | Bug | New | Quan Nguyen Anh | 1 |  | 2017-03-20 10:26 |  |  | 2
816 | [Issue] - Show virtual users instead of thread on front end | 89 | Task | New |  |  |  | 2017-03-21 15:05 |  |  | 2
823 | [Bug] - Automate generate CSV file If it config in Listener | 89 | Bug | New |  |  |  | 2017-03-22 16:36 |  |  | 2
789 | [Analyze] - Report Analysis | 89 | User Story | New | My Dang Thi Thao |  |  | 2017-03-21 13:41 |  |  | 2 | 2
805 | [Research] - Active thread formula | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-03-21 14:03 |  | 2 | 2
806 | [Research] - Response time formula | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-03-21 14:03 |  | 2 | 2
807 | [Research] - Hits per second formula | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-03-21 14:03 |  | 2 | 2
808 | [Research] - Throughput formula | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-03-21 14:04 |  | 2 | 2
809 | [Task] - Select a math lib | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-03-21 14:05 |  | 2 | 2
810 | [Task] - Get familiar with the math lib | 89 | Task | New | My Dang Thi Thao | 3 |  | 2017-03-21 14:06 |  | 3 | 2
676 | Issue list | 89 | User Story | New |  |  |  | 2017-02-21 09:08 |  |  | 2
713 | [Issue] - Unclear workflow of Pm | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-02-21 18:21 |  | 2 | 2
714 | [Issue] - Unclear workflow of testers | 89 | Task | New | My Dang Thi Thao | 2 |  | 2017-02-21 18:21 |  | 2 | 2
781 | [Issue] - Should we add paging for project and test list? | 89 | Bug | New | Quan Nguyen Anh |  |  | 2017-03-17 14:43 |  |  | 2
815 | [Issue] - Distributed option should have its own number of thread field | 89 | Task | New |  |  |  | 2017-03-21 14:31 |  |  | 2
791 | [Implement] - Report Analysis | 89 | User Story | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:41 | 2017-04-30 13:03 |  | 2 | 3
797 | [Task] - Show calculated statistics on tables | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:56 | 2017-04-30 13:03 | 7 | 2
798 | Draw non-calculation charts | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:56 | 2017-04-30 13:03 | 7 | 2
799 | [Task] - Make api for real time charts | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 13:57 | 2017-04-30 13:03 | 7 | 2
801 | [Task] - Implement functions for metrics tables | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 14:00 | 2017-04-30 13:03 | 7 | 2
802 | [Task] - Implement queries to find needed data | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 14:00 | 2017-04-30 13:03 | 7 | 2
803 | [Task] - Implement calculation for complex charts | 89 | Task | Closed | My Dang Thi Thao |  |  | 2017-03-21 14:01 | 2017-04-30 13:03 | 7 | 2

## Sprint 16
Quan Nguyen Anh (fixed-term.Quan.NguyenAnh@vn.bosch.com) shared a work item query with a note.
Note:
Sprint Backlogs for Sprint 16 with details
ID | Title | Iteration ID | Work Item Type | State | Assigned To | Remaining Work | Completed Work | Created Date | Closed Date | Original Estimate | Priority | Story Points
897 | [Docs] - Software design | 92 | User Story | Closed | My Dang Thi Thao |  |  | 2017-05-13 11:24 | 2017-05-16 11:56 |  | 2
898 | [Task] - Write software design | 92 | Task | New | My Dang Thi Thao |  | 5 | 2017-05-16 11:55 |  |  | 2
896 | [Docs] - Write User Guide | 92 | User Story | New | Tuan Le |  |  | 2017-05-13 11:22 |  |  | 2
850 | [TestCase] - Write test cases | 92 | User Story | New | Quan Nguyen Anh |  |  | 2017-04-30 14:30 |  |  | 2
895 | [Doc] - Bug Report | 92 | Task | Closed | Quan Nguyen Anh |  |  | 2017-05-07 12:40 | 2017-05-17 11:06 |  | 2
846 | [Docs] - Sign off documents | 92 | User Story | New | Quan Nguyen Anh |  |  | 2017-04-30 14:17 |  |  | 2
851 | [Task] - Define Sign off list | 92 | Task | Closed | Quan Nguyen Anh |  |  | 2017-04-30 14:31 | 2017-05-17 11:07 |  | 2
852 | [Task] - Write content for sign off | 92 | Task | Closed | Quan Nguyen Anh |  |  | 2017-04-30 14:31 | 2017-05-17 11:07 |  | 2
853 | [Task] - Print sign offs | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-04-30 14:31 |  |  | 2
854 | [Task] - Ask for signatures | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-04-30 14:32 |  |  | 2
894 | [Task] - Release Notes | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-05-07 12:39 |  |  | 2
845 | [Portfolio] - Project summary magazine | 92 | User Story | New | My Dang Thi Thao |  |  | 2017-04-30 14:16 |  |  | 2
856 | [Task] - Install InDesign | 92 | Task | New | My Dang Thi Thao |  | 2 | 2017-04-30 14:32 |  |  | 2
857 | [Task] - Learn basic use of InDesign | 92 | Task | New |  |  |  | 2017-04-30 14:33 |  |  | 2
858 | [Task] - Select template | 92 | Task | New |  |  |  | 2017-04-30 14:33 |  |  | 2
859 | [Task] - Brainstorm content | 92 | Task | New |  |  |  | 2017-04-30 14:34 |  |  | 2
860 | [Task] - Outline the content | 92 | Task | New |  |  |  | 2017-04-30 14:34 |  |  | 2
861 | [Task] - Write the content | 92 | Task | New |  |  |  | 2017-04-30 14:34 |  |  | 2
862 | [Task] - Format and design | 92 | Task | New |  |  |  | 2017-04-30 14:34 |  |  | 2
844 | [Docs] - Wrap up all documents | 92 | User Story | New | Quan Nguyen Anh |  |  | 2017-04-30 14:16 |  |  | 2
848 | [Task] - Extract emails | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-04-30 14:28 |  |  | 2
849 | [Task] - Export Docupedia | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-04-30 14:28 |  |  | 2
893 | [Task] - Export OneDrive | 92 | Task | New | Quan Nguyen Anh |  |  | 2017-04-30 14:55 |  |  | 2
899 | [Task] - Index all documents in html | 92 | Task | New |  |  |  | 2017-05-16 11:59 |  |  | 2
843 | [Docs] - Project Closure | 92 | User Story | New | My Dang Thi Thao |  |  | 2017-04-30 14:15 |  |  | 2
863 | [Task] - Create project closure form | 92 | Task | Closed | My Dang Thi Thao |  | 2 | 2017-04-30 14:35 | 2017-05-16 11:59 |  | 2
864 | [Task] - Write content | 92 | Task | New |  |  |  | 2017-04-30 14:35 |  |  | 2
865 | [Task] - Review | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:35 |  |  | 2
842 | [Demo] - Product promotion video | 92 | User Story | New | My Dang Thi Thao |  |  | 2017-04-30 14:11 |  |  | 2
888 | [Task] - Plan for directing the movie | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:43 |  |  | 2
883 | [Task] - Set up After Effect, Camtasia, Audition... | 92 | Task | New | Tuan Le |  |  | 2017-04-30 14:39 |  |  | 2
884 | [Task] - Select templates | 92 | Task | New |  |  |  | 2017-04-30 14:39 |  |  | 2
885 | [Task] - Brainstorm ideas | 92 | Task | New |  |  |  | 2017-04-30 14:40 |  |  | 2
886 | [Task] - Write scripts | 92 | Task | New |  |  |  | 2017-04-30 14:41 |  |  | 2
887 | [Task] - Record product | 92 | Task | New |  |  |  | 2017-04-30 14:42 |  |  | 2
889 | [Task] - Select sound track | 92 | Task | New |  |  |  | 2017-04-30 14:43 |  |  | 2
890 | [Task] - Turn text to speech | 92 | Task | New |  |  |  | 2017-04-30 14:44 |  |  | 2
891 | [Task] - Edit video | 92 | Task | New |  |  |  | 2017-04-30 14:44 |  |  | 2
892 | [Task] - Review | 92 | Task | New |  |  |  | 2017-04-30 14:45 |  |  | 2
841 | [Poster 10%] - Design poster | 92 | User Story | New | My Dang Thi Thao |  |  | 2017-04-30 14:09 |  |  | 2
875 | [Task] - Set up InDesign, Photopshop, Illustrator | 92 | Task | New | Tuan Le |  |  | 2017-04-30 14:38 |  |  | 2
876 | [Task] - Read requirements | 92 | Task | Closed | My Dang Thi Thao |  | 2 | 2017-04-30 14:38 | 2017-05-17 17:47 |  | 2
877 | [Task] - Brainstorm ideas | 92 | Task | New |  |  |  | 2017-04-30 14:38 |  |  | 2
878 | [Task] - Outline content | 92 | Task | New |  |  |  | 2017-04-30 14:38 |  |  | 2
879 | [Task] - Write content | 92 | Task | New |  |  |  | 2017-04-30 14:38 |  |  | 2
880 | [Task] - Format and Design | 92 | Task | New |  |  |  | 2017-04-30 14:39 |  |  | 2
881 | [Task] - Review | 92 | Task | New |  |  |  | 2017-04-30 14:39 |  |  | 2
882 | [Task] - Edit after review | 92 | Task | New |  |  |  | 2017-04-30 14:39 |  |  | 2
840 | [TestPlan] - Create Test plan | 92 | User Story | New | Quan Nguyen Anh |  |  | 2017-04-30 14:07 |  |  | 2
871 | [Task] - Set up test plan file | 92 | Task | Closed | Quan Nguyen Anh |  |  | 2017-04-30 14:36 | 2017-05-17 11:07 |  | 2
872 | [Task] - Edit content | 92 | Task | New |  |  |  | 2017-04-30 14:37 |  |  | 2
873 | [Task] - Format | 92 | Task | New |  |  |  | 2017-04-30 14:37 |  |  | 2
874 | [Task] - Review | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:37 |  |  | 2
837 | [Reflective 15%] - Write reflective report | 92 | User Story | New | My Dang Thi Thao |  |  | 2017-04-30 13:05 |  |  | 2
866 | [Task] - Read requirements | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:35 |  |  | 2
867 | [Task] - Brainstorm ideas | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:35 |  |  | 2
868 | [Task] - Outline structures | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:36 |  |  | 2
869 | [Task] - Write content | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:36 |  |  | 2
870 | [Task] - Wrap up | 92 | Task | New | My Dang Thi Thao |  |  | 2017-04-30 14:36 |  |  | 2
838 | [Reflective 15%] - Write refletive report | 92 | User Story | New | Tuan Le |  |  | 2017-04-30 14:03 |  |  | 2
839 | [Reflective 15%] - Write refletive report | 92 | User Story | New |  |  |  | 2017-04-30 14:03 |  |  | 2