## Sheet1
Stakeholders | Project Team |  |  |  | Customer |  |  | Support functions | Management Support
Activities | Project Manager | Team Members / Scrum Team |  | Scrum Master | Validation Team |  | Product Owner | Training |  | Group Mgr. | School Supervisors | School Coordinator | School Coordinator
Names | Mr To Hoa Duy Man | Nguyen Anh Quan |  | Ms Dang Thi Thao My | ETI14 Associates |  | Mr To Hoa Duy Man | ETI1 Associates |  | Mr Nguyen Huu Khiem | Mr Truong Phuoc Loc | Mr Lam Quang Vu | Mr Duong Viet Quoc Hoang
|  | Bui Nguyen Thien Khanh | [9 empty] | Mr Petteri Kaskenpalo
|  | Le Huynh Anh Tuan | [9 empty] | Mr Leo Hitchcock
Project Management
Project Planning | C | R |  | R/A | - |  | C | - |  | I | C/I | I | I
Project Monitoring and Control | A | R |  | R | I |  | C | - |  | - | C/I | I | I
Training | C | I |  | I | - |  | C | S |  | - | I | I | I
Decision Analysis and Resolution | A | R |  | R | - |  | C | - |  | - | - | - | I
Configuration Management | A | R |  | R | - |  | C | - |  | - | - | - | I
Risk Management | A | R |  | R | - |  | C | - |  | - | I | I | I
Project Mgmt. Review | A | R |  | R | - |  | C | - |  | I | C/I | I | I
Joint Reviews / Sprint Review | A | R |  | R | - |  | C | - |  | - | I | - | I
Quality Assurance | A | R |  | R | I |  | C | - |  | - | C/I | I | I
Closure | A | R |  | R | I |  | C | - |  | I | C/I | I | I
<Other Activities>
Engineering /Development | Scrum Master | Scrum Team | Customer |  | School Supervisor | School Coordinator |  | Group Manager | Advisor
Requirements | - | - | R |  | I | - |  | - | I
Design | A | R | - |  | I | - |  | - | I
Coding / Task Execution | A | R | - |  | I | - |  | - | I
Integration (if applicable) | A | R | - |  | I | - |  | - | I
Test Specification Preparation
Unit | A | R | - |  | S | - |  | - | I
Integration | A | R | - |  | S | - |  | - | I
System | A | R | - |  | S | - |  | - | I
Test Execution
Unit Testing | A | R | - |  | I | - |  | - | -
Integration Testing | A | R | - |  | I | - |  | - | -
System Testing | A | R | - |  | I | - |  | - | -
Technical Reviews |  | R
Requirement Review | A | R | - |  | I | I |  | I | I
Design Review | A | R | - |  | I | I |  | I | I
Code Review | A | R | - |  | I | I |  | I | I
Test Specification Review | A | R | - |  | I | I |  | I | I
Maintenance and Release
Release | A | R | I |  | I | C |  | I | I
Maintenance | A | R | I |  | I | I |  | I | I
Sprint Planning | A | R | I |  | I | - |  | - | -
<Other Activities>
Legend
R – Responsible - | Who is Responsible for seeing the task through to conclusion?
A – Authority/Approval - | Who has Authority to make the final decision?
S – Supportive - | Who provides Support to the person who has overall responsibility?
C – Consulted - | Who is to be Consulted during the process?
I – Informed - | Who is to be Informed at the conclusion of the process?