## Template_History (hidden)
Open Point List Template
Status: | Approved
Note: Replace the above contents with project specific status and date
Approved by: | Management Representative
Released by: | QEMS Documentation Controller
Note: Replace the above contents with project specific information
Internal / Confidential / Strictly Confidential
Revision History
Verison No. | Modifications | Author | Date
1 | Initial Version | EPG | 2002-07-01
1.1 | Existing fields modified to provide more clarity | Subramaniam K V | 2005-10-10
1.2 | - Reviewed for currency - Added a revision history sheet for projects | Swathy Sunder | 30/09/2010
1.3 | Added: - Ageing Analysis column to calculate the age of each open point - Remarks Column | Mythili Kadiri | 26/06/2013

## Revision History
Open Point List
Status: Valid
Note: Please update the current status above
Approved by :
Released by :
Internal
Note: Please select the document confidentiality level above
Document Revision History
Version No. | Modifications | Author | Date
1 | Initial | My Dang | 2016-10-10
1.1 | Add issues | Scrum team | 2016-10-25

## OPL
|  |  | Open Point List - Capstone PTD |  | Status as on : | 2017-01-05
OPL/Capstone
Sl. No. | Trigger | Opening Date | Issue Description | Proposed Action Point | Resp. | Due Date | Closure Date | Status | Results (what action was actually taken to close the issue) | Remarks
1 | Daily Team Meeting | 13-Otc-16 | Collaboration tool don't use google driver. It not match with BOSCH poilicy | Concern | Khanh Bui | 13-Otc-16 | 13-Otc-16 | Closed | Team will use internal Bosch one drive to store document for study: https://mysites.inside-share.bosch.com/my/dma81hc/Documents/Forms/All.aspx?RootFolder=%2fmy%2fdma81hc%2fDocuments%2fShared%20with%20Everyone&FolderCTID=0x01200044E75C613FEC9541A1D949F8BAE4774C
2 | Daily Team Meeting | 24-Otc-16 | Why new ftl page can not realize tag from tablib library | Research new technologies | Khanh Bui | 25-Otc-16 | 2016-10-25 | Closed | Please visit TFS for solution: https://validationservices.visualstudio.com/EI-300013_Bosch_CapStone/EI-300013_Bosch_CapStone%20Team/_workitems?id=228&triage=true&_a=edit
3 | Validation Team meeting | 2016-11-14 | How we can use ILM for configuration Management | Documenting Proposal | Khanh Bui | 2016-11-15 | 2016-11-15 | Closed | https://inside-ilm.bosch.com/irj/go/nui/sid/407749f1-cb0d-3410-2095-abdb8d8d5c42
4 | Sprint Review meeting | 2016-11-20 | How many kind of report need to draw graph on report page | Develop View report chart | Khanh Bui | 2016-12-03 | 2016-12-03 | Closed | Please visit MoM for detail: https://inside-docupedia.bosch.com/confluence/display/ROJD/Sprint+4+-+Sprint+Review
5 | Daily Team Meeting | 2016-01-10 | What is the maximum number of transactions per test script | Develop View report chart | Khanh Bui | 2016-02-01 | 2016-12-04 | Closed | The number of transaction per test script is dymanic and depend on each test scenario.
Note on B3: What was the source of identification of the issue? (in team meetings,phase review meetings,etc.,)
Note on C3: Recommended date format: dd-mmm-yy
Note on G3: Recommended date format: dd-mmm-yy
Note on H3: Recommended date format: dd-mmm-yy
Note on K3: in case of: - due date change - longer age of an open item than expected - others