## Sheet1
Stakeholders | Project Team | Customer | Management Support |  |  | Legend
[6 empty] | R – Responsible | Who is Responsible for seeing the task through to conclusion?
|  |  | Bosch Mentor | Supervisor | School Coordinator | A – Authority/Approval | Who has Authority to make the final decision?
Name | Pham Huynh Tri Minh Nguyen Trong Tri | Hoang Le Minh | Vo Dong Thanh Tin | Le Ngoc Son | Mr. Petteri Kaskenpalo Mr. Lam Quang Vu Mr. Duong Viet Quoc Hoang | S – Supportive | Who provides Support to the person who has overall responsibility?
[6 empty] | C – Consulted | Who is to be Consulted during the process?
[6 empty] | I – Informed | Who is to be Informed at the conclusion of the process?
Project Management
Project Planning | R | A | C | C | I
Project Monitoring and Control | R | - | C | C | I
Training | - | - | - | C | C
Decision Analysis and Resolution | R | A | C | C | C
Configuration Management | R | A | - | I | I
Risk Management | R | I | C | C | I
Project Management Review | R | A | R | R/C | I
Joint Reviews / Sprint Review | R | R | R | R | R
Quality Assurance | R | A | I | R | I
Closure | R | A | C | C | I
Requirements | R | A | C | C | I
Design | R | - | I | I | -
Coding / Task Execution | R | - | C | C | -
Integration (if applicable) | - | - | - | - | -
Test Specification Preparation | R | A | I | I | S
Integration | - | - | - | - | -
System | R | I | I | C | I
Test Execution
Unit Testing | R | - | I | C | -
Integration Testing | - | - | - | - | -
System Testing | R | I | I | C | I
Technical Reviews | R | - | - | C | I
Requirement Review | R | A | C | C | I
Design Review | R | A | C | C | I
Code Review | R | A | C | C | I
Test Specification Review | R | A | C | C | I
Maintenance and Release
Release | R | A | I | I | I
Maintenance | R | - | - | - | -
Sprint Planning | R | I | C | C | I
<Other Activities>

## Sheet2
Project Planning
Project Monitoring and Control
Training
Decision Analysis and Resolution
Configuration Management
Risk Management
Project Mgmt. Review
Joint Reviews / Sprint Review
Quality Assurance
Closure
<Other Activities>
Engineering /Development
Requirements
Design
Coding / Task Execution
Integration (if applicable)
Test Specification Preparation
Unit
Integration
System