## Sheet1
Agenda | [5 empty] | Project Manage Tool
Detail of each task is here
Week | From | To | Task | Output | Status | Event | 2017-11-03 |  | Proposal
1 | 2017-10-16 | 2017-10-20 | Setup workplace. | None | Done |  | 11-12/1/2018 |  | Informal review
2 | 2017-10-23 | 2017-10-27 | Research Blockchain, Voting process. | PDF | Done |  | 2018-03-21 |  | Formal QR review
3 | 2017-10-30 | 2017-11-03 | Proposal | PDF, PPTX | Done |  | 2018-06-04 |  | Defense Ceremony
4 | 2017-11-06 | 2017-11-10 | Applying Blockchain technology to Voting process. Research about business problems. | PDF | Done | Stakeholders | Client |  | Hoang Le Minh
[7 empty] | Supervisor |  | Le Ngoc Son
5 | 2017-11-13 | 2017-11-17 | Research and use a tool to manage the project. | PDF, Create a project | Done |  | Mentor |  | Vo Dong Thanh Tin
6 | 2017-11-20 | 2017-11-24 | Research and try some open source of blockchain technology. | Code, PDF, Source | Done |  | Member |  | Nguyen Trong Tri
7 | 2017-11-27 | 2017-12-01 |  |  |  |  | Member |  | Pham Huynh Tri Minh
8 | 2017-12-04 | 2017-12-08 | Select an open source and learn more about it (concept, technical,…). | Code, PDF, Source | Done
9 | 2017-12-11 | 2017-12-15 | Design an UI/UX system, learn if needed. Design a process, a workflow for the system. | An UI/UX website, PDF A photo of process, workflow | Done | Meeting at Bosch
[6 empty] | 14/11/2017 |  | Present: What is Blockchain? Apply for Voting? Problems.
10 | 2017-12-18 | 2017-12-22 | Create and config a blockchain private network. | A private network at Bosch | Done
11 | 2017-12-25 | 2017-12-29 | Create nodes in a private network. | Nodes can talk to each other | Done | 22/12/2017 |  | Demo: What have been done?
12 | 2018-01-01 | 2018-01-05 | Create a shared decentralized database. | Read, Write but can't change after saved it. | Done | 2018-08-01 |  | Blockchain introduction in concept
[6 empty] | 22/1/2018 |  | Introduction to Ethereum - Smart Contract -Dapp
13 | 2018-01-08 | 2018-01-12 | Informal review | PDF, PPTX, Code | Done
14 | 2018-01-15 | 2018-01-19 | B: Make rules, conditions and the way of running a smart contract. F: Create Home - Discover - Rooms - Q&A page | PDF | B: Done F: Done | 26/1/2018 |  | Workshop at Bosch
[6 empty] | 2018-02-02 |  | Present: Area - Voting
[6 empty] | 2018-02-03 |  | Demo - Beta Version
15 | 2018-01-22 | 2018-01-26 | B: Create functions to check one-person-one-account of smart contract, make a test case and test. Connect the backend code with the frontend. F: Connect Front - Back and use promise, async method. Create Login Screens, Register Screens, User Screens. | Code, PDF | B: Done F: Done | 2018-06-04 |  | Release Product at Bosch
*Note: For a backup time, if the task is complete, we can skip it and go to the next task. If we finish all the tasks before the end of this project, we will write a tutorial (Knowledge - Building) about how we build this system.
16 | 2018-01-29 | 2018-02-02 | B: Create functions to vote and calculate ballots when the polling is end, make a test case and test. F: Create Vote Room Screens Extra: Write a post to introduce blockchain. | Code, PDF, Solution | B: Done F: Done E: Done
17 | 2018-02-05 | 2018-02-09 | B: Test all functions, list of things needs to be fixed and upgraded. F: Create Result Screens. | Nodes can use and write in the database. | B: Done F: Done
18 | 2018-02-12 | 2018-02-16 | (Backup Time - Research for solution if errors) Febuary 14 - 20: Moon New Year | Code, PDF, Solution | Done
19 | 2018-02-19 | 2018-02-23
20 | 2018-02-26 | 2018-03-02 | Complete the beta version to demo with clients, list features to improve. | A web application. | Done
21 | 2018-03-05 | 2018-03-09 | B: Improve "Multi Question and Option". F: Update create room screen (Type, Invite, Multi), Popup result. | Code, PDF | Done
22 | 2018-03-12 | 2018-03-16 | B: Login with ID instead of address. F: Editing content in each screens. | Code, PDF | Done
23 | 2018-03-19 | 2018-03-23 | Formal QR review | PDF, PPTX, Code | Done
24 | 2018-03-26 | 2018-03-30 | B: Inform result to all the voters/ Invite voters to a room. F: User Info - History Screen | Code, PDF | Done
25 | 2018-04-02 | 2018-04-06 | Environment, System Design, RACIS, Proposal, User Guild, Project Charter and Technical Documents | PDF | On-Going
26 | 2018-04-09 | 2018-04-13 | Issue Log, Proposal Solution, Risk management, ORCS | PDF | not yet started
27 | 2018-04-16 | 2018-04-20 | Sprint Backlog, System Process, SRS, Performance Mesurement and Team Charter | PDF | not yet started
28 | 2018-04-23 | 2018-04-27 | QA&QC, Defense Presentation, Poster and Change Request | PDF | not yet started
29 | 2018-04-30 | 2018-05-04 | Prepare documents for Bosch and Defense | Upgrade a web application. | not yet started
30 | 2018-05-07 | 2018-05-11 | Prepare documents for Bosch and Defense | Code, PDF, Solution | not yet started
31 | 2018-05-14 | 2018-05-18 | Complete all needed documents. | PDF | not yet started
32 | 2018-05-21 | 2018-05-25 | Review with Stakeholders and Close the Project | PDF, PPTX, Code | not yet started
33 | 2018-05-28 | 2018-06-01 | Prepare for Defense Ceremony. | PPTX | not yet started
34 | 2018-06-04 |  | Defense Ceremony | PDF, PPTX, Code | not yet started